## Slide 1: NOAA HFIP High-Resolution Hurricane Test -update -
Ligia Bernardet
Feb 19, 2009

## Slide 2: HRH Test
Goals
  Evaluate the effect of increasing horizontal resolution within a given model on hurricane intensity forecasts
  Provide a data set to explore the potential value of a multi-model ensemble for improving hurricane forecasts
Participants:
  6 modeling groups (URI: GFDL, UWM: UW Non-hydro Modeling System, AOML: WRF-NMM, NRL: COAMPS, MMM: WRF-ARW, PSU: WRF-ARW)
  WRF Developmental Testbed Center (DTC)
  National Hurricane Center (NHC)

## Slide 3: Pre-Test preparations at DTC
Finalized prioritized list of cases (10 storms – 69 cases)
Created archive of input and verification datasets
Determined method for transferring files to/from modeling groups and DTC
Arranged computer resources for some modeling groups
Developed Output Module (OM)
Obtained / ported / adapted / developed / automated verification tools
  GFDL Tracker – many changes for high-res moving nests (collaboration with Tim Marchok of GFDL)
  NHC Verification
  Rapid Intensification / Weakening (RI/RW) verification
  Graphics (NCAR Command Language)
  Archival

## Slide 4: Timeline
Original Timeline
  Forecasts delivered to DTC September 2008 – January 2009
  Workshop and Final Report – March 2009
Final Report (HFIP - Fred Toepfer) – June 2009
Workshop – 7-8 May 2009
Delivery of all runs to be analyzed for Workshop – April 2009
Delivery of all runs to be analyzed for Report – May 2009
Final tests of I/O implementation – March 2009
Revised Timeline

## Slide 5: Status – February 18, 2009
Modeling group | Sent DTC test I/O | Iterated with DTC on I/O | Finalized test I/O | Sent DTC a forecast for evaluation
AOML |  |  |  | 
MMM |  |  |  | 
URI |  |  |  | 
Penn State |  |  |  | 
UWM |  |  |  | 
NRL |  |  |  |