## Slide 1: NOAA HFIP High-Resolution Hurricane Test -update -
Ligia Bernardet
March 19, 2009

## Slide 2: HRH Test
Goals
  Evaluate the effect of increasing horizontal resolution within a given model on hurricane intensity forecasts
  Provide a data set to explore the potential value of a multi-model ensemble for improving hurricane forecasts
Participants:
  6 modeling groups (URI: GFDL, UWM: UW Non-hydro Modeling System, AOML: WRF-NMM, NRL: COAMPS, MMM: WRF-ARW, PSU: WRF-ARW)
  WRF Developmental Testbed Center (DTC)
  National Hurricane Center (NHC)

## Slide 3: Pre-Test preparations at DTC
Finalized prioritized list of cases (10 storms – 69 cases)
Created archive of input and verification datasets
Determined method for transferring files to/from modeling groups and DTC
Arranged computer resources for some modeling groups
Developed Output Module (OM)
Obtained / ported / adapted / developed / automated verification tools
  GFDL Tracker – many changes for high-res moving nests (collaboration with Tim Marchok of GFDL)
  NHC Verification
  Rapid Intensification / Weakening (RI/RW) verification
  Graphics (NCAR Command Language)
  Archival

## Slide 4: Timeline
Original Timeline
  Forecasts delivered to DTC September 2008 – January 2009
  Workshop and Final Report – March 2009
Final Report (HFIP - Fred Toepfer) – June 2009
Workshop – 7-8 May 2009
Delivery of all runs to be analyzed for Workshop – April 08 2009
Delivery of all runs to be analyzed for Report – May 2009
Final tests of I/O implementation – March 2009
Revised Timeline

## Slide 5: Status – March 18, 2009
Modeling group | Sent DTC test I/O | Iterated with DTC on I/O | Passed test I/O for at least one resolution and one lead time | Sent DTC a set (126-h forecast, 30 min, at least 2 resolutions)
AOML |  |  |  (excp need precip) | 
MMM |  |  |  | 
URI |  |  |  | 
Penn State |  |  |  | 
UWM |  |  |  | 
NRL |  |  |  | 

## Slide 6: Current Work at the DTC
Evaluating new test files every week and assisting modeling groups
  Grid navigation problems
  Fields with unrealistic min/max
  Proper representation of missing values
  Time stamp issues
  Challenges with tracking
  Cases that start as tropical depression are difficult to track
  Finalizing automation
  Hoping for production cases delivered by April 08 deadline to have critical mass of results to hold workshop in May.