## Slide 1: Summary and Discussion Next Steps
Bob Gall
HFIP Annual Review Meeting
Miami
Nov 9, 2010
Notes: <number>

## Slide 2: Next Steps-Teams (Stream 2)
Teams will prepare FY11 strategy and milestone/deliverable document similar to last year (Jan 1, 2011)
Overall HFIP milestone/deliverable document prepared by PO (Feb 1, 2010)
  Iterations with the teams
Teams prepare FY 10 accomplishments document (~5-10 pages, 3-5 figures—Jan 1 2011).
Overall HFIP annual report prepared by PO
  Iterations with the teams
Budget for Labs, Navy and DTC prepared by PO
Final budgets released late March
Notes: <number>

## Slide 3: Next Steps-Universities
This year we will use a competitive process for distribution funding to the various universities
Announcement of Opportunity released ~ Jan 1 , 2011
Proposals due in PO ~ Feb 1 2010
Review and recommendations from Review panel ~March 1, 2011
Awards released when overall HFIP funding is announced in late March.
Approximately $1M in funding available (award range $50K-$100K)
Process led by Naomi Surgi
Funding available for work on Streams, 1.0, 1.5, 2.0
This path is available to any organization for which we don’t have a direct funding path (primarily universities)
Notes: <number>

## Slide 4: Next Steps—Stream 1.0
Final approval of OHMD process by HEOB~Dec. 1, 2010
OHMD management panel formed, Dec 2010.
Management panel meets mid January
  Review past results from FY10 operational models
  Recommend specific stream 1 projects for FY11
  Discuss operational implementation for FY11
    Final decision by EMC
  Recommend participating Stream 1 organizations for FY11
Final Stream 1 funding decisions by PO announced in late March.
Notes: <number>

## Slide 5: Next Steps—Stream 1.5
Stream 1.5 process published on the HFIP website (mid Nov, 2010)
Candidate stream 1.5 candidates identified
  Participating organizations must be willing to perform the minimum number of retro runs. ~Dec 1 2010
    Would like to see both regional amd global models included
DTC oversees retro tests for 1.5 and manages repository of results
DTC publishes Stream 1.5 retro test results ~April 1, 2011.
NHC announces its selection of Stream 1.5 and its rational for selection.
  Published on HFIP website.
Note: regional models not selected for stream 1.5 will be part of the FSU Correlation Based Consensus multi-model ensemble.
  Others could also be included if they can provide adequate results from previous years.
Stream 1.5 runs will begin August 1, 2010. T-jet will be available for these runs.
Process is Led by Ed Rappaport
Notes: <number>