## Slide 1
Sensing Hazards with Operational Unmanned Technology (SHOUT)
Mission Readiness Review
DATE

## Slide 2: Agenda
AGENDA
Opening/Introducton Remarks Phil Kenul/Gary Wick
Management & Logistics Phil Kenul
Tropical Outlook Jason Dunion
Mission & Science Overview Gary Wick
Flight Patterns & Modules Jason Dunion
Data Management & Analysis JC Coffey
GH Operations Jon Neuhaus
Actions Phil Kenul

## Slide 3: INTRODUCTION
Name : SHOUT (Sensing Hazards with Operational Unmanned Technology)
When: 16 August – 30 Sepember 2015 (with up to a 2 week extension-Flight ops nominally 25 August-27 September)
Where: NASA Wallops Island Flight Facility, Virginia
  Demonstrate and test UAS concept of operations that could be used to mitigate the risk of diminished high impact weather forecasts and warnings in the case of polar-orbiting satellite

## Slide 4: Overview: SHOUT Science Objectives
Objective 1 - Quantify the significance of unmanned observations to high impact weather prediction through data impact studies using Observing System Experiments (OSE) based on unmanned observations collected during prototype operational field missions and Observing System Simulation Experiments (OSSE) based on expected unmanned observing capabilities.
Objective 2 - Quantify the cost and operational benefit of unmanned observing technology for high impact weather prediction through detailed analysis of life-cycle operational costs and constraints versus scientific benefit.

## Slide 5: SHOUT
Project Management & Logistics
Philip Kenul
Project Manager

## Slide 6
Robbie Hood, Director UAS Program, NOAA OAR
Gary Wick, PI, Mission Scientist, NOAA ESRL
Jason Dunion, Deputy PI, Deputy Mission Scientist, NOAA HRD
Philip Kenul, Project Manager, NOAA OAR, Trivector Services
JC Coffey, Deputy Project Manager, NOAA OAR, CNT
Quincy Allison, Deputy Program Manager, Ames Research Center
Frank Cutler, GH Project Manager, AFRC
Jon Neuhaus, GH Deputy Project Manager, AFRC
Mark Buschbacker, GH Payload Manager, AFRC
Ron Walsh, SHOUT Wallops PM, WFF
Denise Lawless, SHOUT Wallops Deputy PM
SHOUT Mission Management

## Slide 7: SHOUT Management
Program Manager : Robbie Hood/UASPO
Overall Directions & Planning
Mission Systems Engineer
Deputy PM: JC Coffey/UASPO
Mission Requirements
Project Manager: Philip Kenul/UASPO
Budget & Schedule, Mission Operations &
Deployment Operations
Principal Investigator : Gary Wick/ESRL; Mission Science: Jason Dunion AOML-HRD
Science Requirements – Mission Planning
Flight Planning & Analysis
Aircraft Manager
Frank Cutler/AFRC
GH Management
Payload Manager
Mark Buschbache r
Modifications/Integration
Data Management
JC Coffey & ESRL-GSD
Data Archival /Access
WFF Manager
Ron Walsh/WFF
Facilities & Infrastructure
Dropsondes
Hock (NCAR)
HIWRAP
Heymsfield (GSFC)
HAMSR
Lambrigtsen (JPL)
LIP
Blakeslee (MSFC)
AV-6

## Slide 8: FINANCIALS

## Slide 9: Interagency Cooperation NASA / NOAA / USAF 2015 Hurricane Research Tri-Agency Communications Plan

## Slide 10: SHOUT Air Force/ONR /NOAA Coordination to improve tropical storms observations Operation Base Locations
NASA
WFF
AFRC/53rd WRS
Keesler AFB
NOAA/AOC
MacDill AFB
STX
TBPB
BDA
*
NASA JSC
Ellington Field

## Slide 11: http://uas.noaa.gov/shout

## Slide 12: Lodging and Badging
Room blocks established at per diem
  Comfort Suites
  Best Western
  Fairfield Inn
  Call hotels directly; mention NOAA/NASA SHOUT
Eagle’s Nest
  PIV badges and CAC card holders only
Badging at both AFRC and WFF managed via ESPO database
  Groups populated
  Please enter travel plans ASAP-Need specific on site dates
  Multiple visit capability at both sites

## Slide 13: COMSEC
COMSEC procedures in effect at both sites
WFF training from last year valid for two years
Sharing WFF hangar with Navy
  No additional COMSEC required during while NAVY Ops are conducted.

## Slide 14: SHOUT Risks for 2015
Reliability – AV-6 will be used. AV-1 is being retired (?).
IAA’s: Delays in cost estimates for GSFC under AFRC IAA may impact timely approvals/Funds transfer. MSFC IAA Pending.
Instrumentation – All Instrument payloads previously flown and required minor effort. No major problems are currently apparent.
  LIP Delay Nose Probe install
  HIWARP/AVAPs delayed arrival at AFRC (7/20/15)
Flight Ops Restrictions – Standard issues with clearances approvals, VACAPES conflicts.
Quiet Atlantic Basin/Redeploy –Lost time to project will reduce productivity if Atlantic basin quiet. Costs of redeploy should be minimal and fund adequate.

## Slide 15: Operations
Deployment Decision
  KDP 1 on July 28/29 Go/NO GO to WFF
Redeployment to AFRC
  KDP 2 on September 7
  Approx 6-7 days to move operations

## Slide 16: Timeline and Deployment Plan

## Slide 17
June 2015 |  |  |  |  |  | 
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
 | 1 | 2 | 3 | 4 | 5 RDO | 6
7 | 8 | 9 | 10 | 11 | 12 | 13
14 | 15 | 16 | 17 | 18 | 19 RDO | 20
21 | 22 | 23 | 24 | 25 | 26 | 27
28 | 29 | 30 |  |  |  | 
NOAA SHOUT’15 GH Project Schedule
AFRC / WFF
Final 2Jul’15
Neuhaus
872 Flight Ready
Pilot Prof Flt
Pilot Prof Flt
AFRC ORR
Lessons Learn Table Top
ORR Slide Review

## Slide 18
July 2015 |  |  |  |  |  | 
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
 |  |  | 1 | 2 RDO | 3 HOLIDAY | 4
5 | 6 | 7 | 8 | 9 | 10 | 11
12 | 13 | 14 | 15 | 16 | 17 RDO | 18
19 | 20 | 21 | 22 | 23 | 24 | 25
26 | 27 | 28 | 29KDP1 | 30 | 31 RDO | 1
GH Crew – Prep Aircraft and Hangar for SHOUT -- Install AVAPS Mount, Z-61
HWRAP/AVAPS OA Harnessing / Cleanup
LIP Instrument
Arrives AFRC
*Note: “SIL Bench Tests” includes Wt., SIL Power Tests, and Data-IT Tests
Wt & Bal
LIP Unpack, Test
SIL* Bench Tests
NOAA SHOUT’15 GH Project Schedule
AFRC / WFF
HIWRAP / AVAPS installation on A/C
Fuel A/C
HIWRAP/AVAPS Teams Arrives
LIP Team Arrives
LIP install on A/C
HIWRAP AVAPS Inst’s Arrive AFRC
HAMSR Arrives, SIL* Bench
HAMSR Install on A/C
HIWRAP / AVAPS Unpack, Test
SIL* Bench Tests
LIP install on A/C
LIP OA Harnessing / Cleanup
Hangar IT Testing
Hangar IT Testing

## Slide 19
August 2015 |  |  |  |  |  | 
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2 | 3 | 4 | 5 | 6 | 7 | 8
9 | 10 | 11 | 12 | 13 | 14 RDO | 15
16 | 17 | 18 | 19 | 20 | 21 | 22
23 | 24 | 25 | 26 | 27 | 28 RDO | 29
30 | 31 |  |  |  |  | 
Initial Data-IT & Instr. Teams- WFF
Science Flight Ops
Instr. Outdoor SATCOM Testing (w/GHOC-E manned)
Range Flt (6 hrs)
Pre-CST
CST
Inst. & A/C Preflights
Inst. & A/C Preflight
Science Flight Period
NOAA SHOUT’15 GH Project Schedule
AFRC / WFF
Tech Brief
Remaining GH Crew, GH Team & Inst. P.I.’s to WAL
2 trucks leave for WFF
Atlantic Ku Sat Support Starts
CST Backup
Range Flt (Backup)
Inst. & A/C Preflight
Inst. & A/C Preflight
Transit Flt. (Backup)
Instrument Access
Initial GH OM Crew to WFF
Inst. & A/C Preflight
Instrument Access
Transit Flt. to WAL
Initial GH Flt. Crew to WFF
1 trucks to WFF
Pacific Ku Sat Support Starts
Lessons Learn Table Top

## Slide 20
September 2015 |  |  |  |  |  | 
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
 |  | 1 | 2 | 3 | 4 | 5
6 | 7KDP-2 HOLIDAY | 8 | 9 | 10 | 11 RDO | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 RDO | 26
27 | 28 | 29 | 30 |  |  | 
Science Flight Period
Science Flight Period
Science Flight Period
Science Flight Period
Science
NOAA SHOUT’15 GH Project Schedule
AFRC / WFF
Transit Flt. to EDW
Inst. Removal & Packing
GH Team & Inst. P.I.’s AFRC
Earliest decision point to RTB
*Note: The first Pacific science flight after returning from Wallops is estimated to be 5 to 8 days following return.
*Earliest date to begin Pacific Ops
Pacific Option - Science Flight Period
Pacific Option - Science Flight Period
Pacific Option - Science

## Slide 21
October 2015 |  |  |  |  |  | 
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
 |  |  |  | 1 | 2 | 3
4 | 5 | 6 | 7 | 8 | 9 RDO | 10
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 | 20 | 21 | 22 | 23 RDO | 24
25 | 26 | 27 | 28 | 29 | 30 | 31
Schedule Contingency
NOAA SHOUT’15 GH Project Schedule
AFRC / WFF
Both Atlantic and Pacific Ku Sat Support Ends
Trucks leave WFF for AFRC
Schedule Contingency
Schedule Contingency

## Slide 22: SHOUT PAYLOADS
Investigator | Instrument | Acronym | Primary Measurement
Bjorn Lambrigsten, JPL | HAMSR | High-Altitude MMIC Sounding Radiometer | Profiles of temperature, humidity in non-raining areas; precipitation profiles
Gerry Heymsfield, GSFC | HIWRAP | High-alt. Imaging Wind and Rain Airborne Profiler | 3-D precipitation, winds; sfc winds in non-raining areas
Gary Wick, NOAA | AVAPS | Advanced Vertical Atmospheric Profiling System (dropsonde) | High-resolution profiles of temperature, humidity, and winds
Richard Blakeslee, MSFC | LIP | Lightning Instrument Package | Electric field components, aircraft self-charge, and air conductivity
Notes: Check spelling

## Slide 23: Current Tropical Outlook North Atlantic & Eastern North Pacific
Jason D. Modified
This will need to be updated the day before the MRR

## Slide 24
NOAA
SHOUT
Number of Tropical Cyclones per 100 Years
NOAA SHOUT Science Operations: 25 Aug – 27 Sep 2015
North
Atlantic
Eastern
North Pacific
NOAA
SHOUT
Jason D. Modified

## Slide 25
2015 Tropical Outlook Tropical cyclone Accumulated Cyclone Energy (ACE)
& occurrence of hurricanes after August 1st
El Nino Years
The eastern North Pacific hurricane season is significantly more active overall
The North Atlantic hurricane season is significantly less active overall
North Atlantic tropical cyclone activity drops significantly after September
Jason D. Modified

## Slide 26: SHOUT Science Team Readiness Gary Wick/ Jason Dunion
Mission Scientist’s (MS) roles & responsibilities document prepared (Section 5 SHOUT MOP)
Familiarization/clarification of flight rules, flight scheduling, flight restrictions (Section 3 SHOUT MOP)
GH flight modules compiled and documented (Section 3 SHOUT MOP)
2015 Shout Dry Run
  Aug 10-19, 2015
  Exercise 2015 Wx brief schedule
  Exercising real-time use of adaptive sampling software for targeting GH dropsonde observations
  Exercising of flight planning software, Mission Tools Suite
Data Management Plan submitted
Jason D. Modified

## Slide 27
2015 NOAA SHOUT
Mission Science Schedule
Dry Run: 10-19 August
Dry Run:
1 SHOUT mission scientist assigned each day
1200 EDT HRD map discussion (weekdays)
TCI 1530 EDT map discussions (weekend)
Run GH targeting software in real-time
Prepare Global Hawk boxes (day+2) & tracks (day+1)
Daily 1100 EDT coordination with pilots
Jason D. Modified

## Slide 28
2015 NOAA SHOUT
Mission Science Schedule
Science Operations: 25 Aug – 27 Sep
Science Operations:
0730 EDT: daily cage meeting (shift-1 mission scientists & pilots)
0830 EDT: daily SHOUT coordination call
Wallops local weather (NASA Wallops-led)
MS shift-1: lead with a 5-10 min weather update)
Discussion of flight plans and strategies
1000 EDT: Coordination call with NOAA IFEX & ONR TCI
1100 EDT: Coordination with pilots
1200 EDT: HRD map discussion (weekdays only)
1530 EDT: ONR TCI map discussion (weekends only)
Jason D. Modified

## Slide 29
2015 NOAA SHOUT
Mission Science Schedule
Science Operations: 25 Aug – 27 Sep
Science Operations:
Run HWRF ensemble targeting software in real-time
Prepare Global Hawk flight boxes (day+2) & tracks (day+1)
Mission Science Shifts
MS shift 1: 0400-1300 EDT (2-3 SHOUT)
MS shift 2: 1200-2100 EDT (2 SHOUT + 1 TCI)
MS shift 3: 2000-0500 EDT (2-3 SHOUT)
Jason D. Modified

## Slide 30
2015 NOAA SHOUT
Mission Science Schedule
Extended Science Operations: 28 Sep – 14 Oct
Extended Science Operations:
Same schedule as Science Operations Period
Activated if a potentially high-impact tropical cyclone is imminent and resources are available to support operations
Jason D. Modified

## Slide 31
2015 NOAA SHOUT
Mission Science Scheduling
Mission Science:
Mission Science Shifts
MS shift 1: 0400-1300 EDT (2 SHOUT)
MS shift 2: 1200-2100 EDT (2 SHOUT + 1 TCI)
MS shift 3: 2000-0500 EDT (2 SHOUT)
TCI will have a presence at Wallops and provide 1 mission scientist during shift 2 (Science Ops period)
Please reply to Doodle poll email send by J. Dunion
Provide your total window of availability
Jason will coordinate your actual time commitment
Detailed MS schedule >> 1-2 weeks
DELETE SLIDE

## Slide 32: DAILY MEETING SCHEDULE
TIME EDT | 0600 EDT | 0700 EDT | 730 | 800 | 830 | 900 | 930 | 1000 | 1030 | 1100 | 1130 | 1200 | 1230 | 1300 | 1330 | 1400 | 1430 | 1500 | 1530 | 1600
TIME PDT | 0300 PDT | 0400 PDT | 430 | 500 | 530 | 600 | 630 | 700 | 730 | 800 | 830 | 900 | 930 | 1000 | 1030 | 1100 | 1130 | 1200 | 1230 | 1300
TIME GMT | 1000 GMT | 1100 GMT | 1130 | 1200 | 1230 | 1300 | 1330 | 1400 | 1430 | 1500 | 1530 | 1600 | 1630 | 1700 | 1730 | 1800 | 1830 | 1900 | 1930 | 2000
FORECAST PREPARATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLOBALHAWK STATUS (Cage MTG) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLOBALHAWK INSTRUMENT STATUS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLOBALHAWK FLIGHT PLAN/DROP PREP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WEATHER AND PLANNING DISCUSSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
POD PREP/SUBMIT TO AOC/CARCAH |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NOAA HRD GO/NO GO TELECON |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
INTERAGENCY TELECON |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
FLIGHT CREW ALERT /FLIGHT PLAN SUBMIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NOAA HRD WX BRIEF (WEEKDAY) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NOAA/TCI WX BRIEF (WKENDS/HOLIDAYS) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SHOUT POD |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 33: Pilot /Mission Science Communications
One shift to be flown from AFRC
Flight plan changes anticipated
Initial contact through Mission Director
Sufficient advance notice needed
  Half hour notice required to refile flight plans
  Coordinates for waypoints and dropsonde locations
  Formatting important

## Slide 34
2015 SHOUT
Flight Patterns & Modules
Jason Dunion

## Slide 35
Global Hawk Sample Flight Modules
Advantages
Far Field sampling
Simpler navigation
Disadvantages
Radial/Azimuthal sampling
Long pattern
Limited Inner core snapshots
Radial gradients
HAMSR & HIWRAP >> inner core
On-Station Time
~19.75 hr
R=0 to R=~665 km
12x12 degree box
Lawn Mower (~2 deg spacing)
Jason D. Modified

## Slide 36
Global Hawk Sample Flight Modules
Rotated Butterfly (30 deg)
Advantages
Radial/Azimuthal sampling
Radial gradients
~ 8 center crossings
Inner core & envir sampling
HAMSR & HIWRAP >> inner core
Disadvantages
Not ideal for inner core snapshots
Far field sampling limited
Navigating center crossings
On-Station Time
~12.5 hr
R=0 to R=~450 km
Jason D. Modified

## Slide 37
Global Hawk Sample Flight Modules
Advantages
Radial/Azimuthal sampling
2 Inner core snapshots
Radial gradients
9 center crossings
Inner core & environ sampling
HAMSR & HIWRAP >> inner core
Disadvantages
Far field sampling limited
Navigating center crossings
On-Station Time
~14.0 hr (3.25 hr/6.5/3.0 hr)
R=0 to R=~450 km
Butterfly (small-large-small)
Jason D. Modified

## Slide 38
Global Hawk Flight Modules
Adaptive GPS Dropsonde Sampling
Real-time targeting products (based on 80 member HWRF ensemble);
Valid for a Global Hawk mission on 04 August 12 UTC (designed to optimize the 06 August 12 UTC track forecast);
Warmer colors: denote target regions where GPS dropsonde observations could help reduce HWRF track uncertainty;
2014 Hurricane Bertha
Jason D. Modified
Notes: Hypothetical reduction in primary variability axis distance at 1200 UTC 6 August due to assimilating a dropsonde at each point. The warmer the color, the greater the impact. Figure is storm-centered (the x denotes the predicted center of Bertha at the time).

## Slide 39
Global Hawk Sample Flight Modules
Convective Module
~45-60 minute deviation from the main flight pattern: sample convective targets in the tropical cyclone inner core and spiral bands;
Sampling by GPS dropsondes, HAMSR microwave sounder, and HIWRAP dual frequency Doppler radar;
Requires close coordination between mission scientists and Global Hawk pilots;
Jason D. Added
Notes: Hypothetical reduction in primary variability axis distance at 1200 UTC 6 August due to assimilating a dropsonde at each point. The warmer the color, the greater the impact. Figure is storm-centered (the x denotes the predicted center of Bertha at the time).

## Slide 40
2015 SHOUT
Flight Planning Tool: HRD tkmap
Jason Dunion

## Slide 41
2015 NOAA SHOUT
HRD tkmap track software
Used by NOAA HRD for P-3 and G-IV aircraft flight planning for 15+ years;
Runs quickly (few seconds);
Generates aircraft track and GPS dropsonde coordinate files and track graphics;
Output can be quickly uploaded to NASA’s Airborne Science Mission Tools Suite (MTS) >> flight planning and situational awareness;
Jason D. Modified

## Slide 42
2015 NOAA SHOUT
HRD tkmap track software
Track & dropsonde image (png)
Input File (text)
Lat-Lon Points
Jason D. Modified

## Slide 43
Input File (text)
(no motion)
Waypoints File (text)
Dropsonde File (text)
Track & dropsonde image (png)
2015 NOAA SHOUT
HRD tkmap track software
Input File (text)
(motion: 10kt@10deg)
Jason D. Modified

## Slide 44: Data Analysis and Management
STATUS
JC COFFEY

## Slide 45: Data Management and Archival
Formal SHOUT data management plan exists
Team at NOAA ESRL/GSD leading data management
  Integration with NOAA Meteorological Assimilation Data Ingest System (MADIS)
Official NOAA data center to be final archive
  National Centers for Environmental Information
  Products to archive?
  Data to enable model evaluation and validation
Collaboration planned with ONR TCI field catalog from EOL

## Slide 46
ARC
ESPO HS3 Website
Mission Tools Suite
Data
Displaying Navigation and Video
Displaying Instrument data for strip chart plotting
Displaying some Real-time data and Quick Looks on Map
Bookmarks to Real-time data and Quick Looks
Bookmark to Catalog
Catalog (Satellite data during the period of deployment)
Navigation Data
Instrument Status
Video
PI
Science Instrument data
Real-time (during flight)
Quick Looks/derived products (after flight)

## Slide 47
Global Hawk Flight Operation
Jon Neuhaus

## Slide 48
GHOC East at Wallops Flight Facility, Virginia-Readiness
Notes: 48

## Slide 49
Aircraft Flight Control and Air Traffic Control Communications Architecture
Iridium Provides Global Coverage
Encrypted Links are Used for Aircraft Command and Control
Notes: 49

## Slide 50
Payload Communications Architecture
50
Iridium Provides Global Coverage
Notes: 50

## Slide 51: Platform Overview, APCS
Airborne Payload C3 System (APCS) Components and Antenna Locations
3
Zone 7
14
12
Zone 61
1
16
46
Zone 25
22
51
GPS Antenna
Iridium Antennas (6)
Ku Antenna
NASDAT
MPCS
Link Module

## Slide 52
SHOUT 2015 - Payloads
872 (AV-6)
3
7
13( (L) 14 (R)
12
61
16
46
25
22
LIP (left side)
DropSonde Dispensor
HIWRAP
HAMSR
Low-light Camera
LIP
LIP
HDVis Camera
LIP
Storm Scope
GHIS (Accel)
Daylight Camera
LIP (rt. side)
DropSonde Data
AVAPS
HAMSR
HIWRAP
LIP
Airborne Vertical Atmospheric Profiling System
High Altitude MMIC Sounding Radiometer
High Altitude Imaging Wind and Rain Profiler
Lightning (and Electric Field Meas.) Instrument Package

## Slide 53
LIP Instrument Layout on Global Hawk
/Conductivity Probe
Fwd Up
Aft Up
Fwd Down
Aft Down
Conductivity probe not fully integrated for GRIP
Aft Down Field Mill will be moved for SHOUT
Notes: This slide shows how the LIP sensors were distributed about the Global Hawk during GRIP.
The primary change that we will have to make in SHOUT is to move the Aft Downward looking field mill slightly forward since its GRIP location is now occupied by the AVAPS antenna.

## Slide 54
SHOUT 2015 Schedule & Ops Tempo
Single Air Vehicle NASA 872 (AV-6)
Notional Schedule
Ops Tempo
Approx 268 Flight Hours (approx. 10-12 flights)
Flight duration: max 26hrs (weather forecast dependent)
Approximately 1 flight every 2-3 days
Surges: Back to back missions, up to 6 days (24 hr turns)
1 full duty day notification for flight coordination package (2-3 day “heads up”)
*Possible 1 week extension for high impact storm event *
N872NA (AV-6) | 
8/11/2015 | Combined Systems Test
8/13/2015 | AFRC range flight
8/19/2015 | Transit flight to WFF
8/25/2015 | Open science flight window
9/27/2015 | Close science flight window
9/28/2015 | Transit flight to AFRC

## Slide 55
NASA Wallops Flight Facility (WFF)

## Slide 56
WFF Runways
10/28 8000 ft x 200 ft
04/22 8750 ft x 150 ft

## Slide 57
WFF Airspace
  KWFF Class D: 5nm radius from center of airfield, surface – 2500ft AGL
  R-6604 A & B: surface to unlimited – scheduled through WFF
  W-386: surface to unlimited – scheduled through FACSFAC VACAPES (DOD)
R-6604A
R-6604B
W-386
W-386
WFF Class D

## Slide 58
Proposed Equivalent Sense and Avoid Mitigation at WFF
Departures and approaches will mitigate the sense and avoid requirement with a combination of ground observers and chase aircraft.
Ground Observer (Trapper)
  Within 3nm of KWAL and below 3,000 ft
  On airfield in contact with GH Pilot
Chase aircraft with pilot and dedicated observer (2 aircrew)
  Flight outside of SUA and visual range
WFF Equivalent Sense and Avoid

## Slide 59
WFF Flight Departures
  Mission Planning:
  NGC Mission Plan – uses common routing in NAS when possible.
  FASFAC VACAPES - Test Track C/D sub-area developed for NASA Global Hawk in W-386
  Departures:
  Conditions: Day/Night, VMC only
  Operating control tower and visual observer required for all departures
  Chase required to be on standby during departure in case of RTB (2-3 hrs)
  R6604 required exclusive used surface to 10,000 MSL
  Test Track required exclusive use 5,000 MSL to FL450, east W-386 above FL450
  Lost Link Logic has aircraft returning to departure runway
  All departures meet the office of NASA Range Safety population avoidance criteria

## Slide 60
WFF Flight Operations Summary
  Approaches:
  Conditions: Day/Night, VMC+ only
  Operating control tower and chase aircraft required for all approaches & runways
  Chase aircraft will join GH in W-386 in the lower orbit in the VACAPES Test Track Area ‘Charlie’
  Lost Link Logic has aircraft returning to runway 28
  All approaches meet the office of NASA Range Safety population avoidance criteria

## Slide 61
Emergencies
  Emergencies:
  If an emergency RTB back to WFF is declared by the PIC, ATC will provide emergency handling to reduce loss of life and property. PIC will follow emergency procedures checklist. (Non-emergency RTB’s will loiter in Atlantic until tower can open.)
  An emergency landing could occur at night and/or during IMC conditions at WFF or other emergency landing fields.
  Control tower will be staffed for emergency RTB.
  Other emergency landing fields: NAS Pax River, KSC, Cherry Point MAS, Beaufort MAS, NS Mayport, NAS Key West
  AFRC pilots may conduct an emergency landing at WFF in the event that WFF pilots are in crew rest.
  The definition of an emergency is a distress or an urgency condition.

## Slide 62: SHOUT Emergency Landing Sites

## Slide 63
Chase Operations Summary
  Requirements:
  The chase must remain at a safe distance from the aircraft to ensure collision avoidance should a malfunction occur, and must remain close enough to the aircraft to provide visual detection of any conflicting aircraft and advise the PIC of the situation.
  The chase aircraft pilot and observer will not concurrently perform either observer or UAS pilot duties along with chase pilot duties. The chase must maintain direct voice communication with the UAS pilot.
  For approaches, the chase aircraft will rendezvous with Global Hawk in W-386 between 7,000 and 15,000 MSL. The chase will follow Global Hawk through Class E, into Class D airspace and be prepared to continue chase for a go-around contingency.
  Minimum meteorology requirements for Global Hawk operations with chase is VFR. VFR in Class D airspace are 3 statute miles visibility and 1000-foot ceiling. Minimum meteorology requirements for remaining VMC in Class D and Class E airspace (below 10,000 MSL) are 3 statute miles and ability to maintain the follow distance from clouds: 500 feet below, 1,000 feet above, and 2,000 feet horizontal.
  Backup chase capability is highly desirable in case primary chase is unable to fly due to unscheduled maintenance issue. Landing without chase will require Global Hawk pilot to declare an emergency to land.

## Slide 64: SHOUT Science Atlantic Region Overview
SHOUT ATLANTIC Operations Area

## Slide 65
C1/C2 Route
Gulf Science Route
ADIZ
Mexico FIR
Houston FIR
Miami FIR
Gulf of Mexico Route

## Slide 66
Caribbean Route

## Slide 67
Caribbean Route

## Slide 68
Caribbean Route

## Slide 69
Caribbean Route

## Slide 70
10N
Rte A
10N 20W
RTE F
15N
20N
Rte B
25N
30N
Rte C
35N
20N 20W
30N 20W
10N 30W
Rte E
10N 40W
Rte D
All Atlantic Routes
Atlantic Route

## Slide 71
Atlantic Route A

## Slide 72
Atlantic Route D

## Slide 73: Dropsonde System
Agreements between agencies in 2015 Interagency Hurricane Operations Plan (IHOP).
NOTAM published.
Max of 88 dropsondes.
Need to talk to ATC real time (phone) for traffic deconfliction.
Multiple levels of system inhibits to ‘safe’ system.
Pilot in command final release authority.
Extensive mission rules have been agreed upon by all weather aircraft based on dropsonde drift analysis.
Flights scheduled in Tropical POD produced by Chief, Aerial Reconnaissance Coordination (CARCAH), All Hurricanes - National Hurricane Center.

## Slide 74: Miniature In-situ Sounder Technology (MIST) Dropsonde System

## Slide 75
SHOUT Example AV-6 Flight Tracks - Gulf
Over-storm aircraft
Approx. 17 hr pattern
Figure 4 flight pattern
Follows storm direction

## Slide 76
SHOUT Example Flight Tracks – Western Atlantic
Track is for storm similar to Hurricane Isabel in 2003
Storm threatens US
Dropsonde releases

## Slide 77
SHOUT Example Flight Tracks – Central Atlantic
Lawnmower pattern
Tropical disturbance that could eventually become a hurricane
Dropsonde releases

## Slide 78: Flight Coordination – Timeline
T-2 Day
  Flight route determined by science
  Mission Region transmitted to FAA by COB
T-1 Day
  NOTAM for Dropsondes transmitted
  Aviation weather briefing
  ‘T-1’ Crew Briefing, if required
  Aircraft and GHOC preflights
T-0 Day
Takeoff -3 hrs
  Aviation weather briefing
  File DD1801 flight plan
Takeoff -2 hrs
  ‘T-0’ Crew Breifing
  Personnel man GHOC
T-1 hr - Engine start

## Slide 79: Mission Plans
    Route Planning
    Science to post route coordinates to MTS
    Pilots to retrieve coordinates data from MTS
    Pilots to insert coordinates into the Portable Flight Planning System (PFPS)
    PFPS used to generate aircraft flight tracks
    Flight Crew Notification of Route
Nominally, 1.5 duty day notification for flight coordination package (by 1100 local time 1.5 days prior to mission)
      The requirement is for boundaries of the flight region and inbound and outbound routes to be identified.
      More detailed plan submitted up to 24 hrs before flight.
FAA notification required one business day prior to flight
  For Saturday, Sunday and Monday flights, that means that flight plans must be submitted to flight crew by Thursday @ 1100 Local.
Can make changes to filed plan on day of flight (process to be defined but will require direct communication with the flight crew)
    Remember that access to foreign owned FIRS could be an issue on short notice changes
79

## Slide 80: Mission Rules & Go-No go

## Slide 81: Mission Rules
Only authorized personnel are permitted in the Flight Operations Room of the GCS.
  - During critical phases of flight, access to the aircraft command and control side of the GCS is restricted to essential personnel only (i.e. Mission Director, Pilots, GCS Operator, RSO, Senior Ops Rep and personnel undergoing training for any of these positions).
  - Critical phases of flight are defined as flight within R-2515, any test points, any in-flight or ground emergency situation, flight below 10,000 ft or critical mission maneuvers (i.e. vertical maneuvering).
Weather Limits:
  Ground
    Winds: < 15 kts (cross), 30 kts (head), 25 kts (tail)
    No lightning within 5 nm
    Min. RVR - 1 mile
    No standing water reported on the runways
  In flight:
    Do not approach thunderstorms within 25 nm
    No overflight of cumulus tops higher than FL500
    No flight into forecast or reported icing conditions
    No flight into forecast or reported moderate or severe turbulence

## Slide 82: Mission Rules
Aircraft systems:
  Do not switch UHF LOS between LCPs during taxi .
  If GHOC/GHMOF transitions to auxiliary power while AV is taxiing:
      “STOP TAXI’ command will be issued
      “TAXI” command will not be reissued until GHOC/GHMOF returned to primary power
  If GHOC/GHMOF transitions to auxiliary power while AV is in flight, an RTB will be initiated
C1 Contingency timer may be set to 5 minutes or less while the air vehicle is in autonomous mode, and no greater than 1 minute while in override mode within R-2515 and R-2508. C1 Contingency timer will be set IAW COA requirements when outside the Restricted and Warning Area. In override mode, the pilot will maintain an appropriate margin to ensure that if a C1 were to occur, the aircraft would not cross an airspace boundary.
Failure of MPCS, control functions or extended loss of APCS safety-of-flight (SOF) parameters will result in an RTB. Extended loss of APCS SOF parameters for any instrument will result in removal of power for that instrument.
Aircraft to be operated within the temperature limits defined in the Global hawk Flight Manual
  Standardly available JP5 fuel to be used (not extreme cold tested fuel)

## Slide 83: SHOUT Aircraft De-Confliction Plan
Communications plan includes chat details and aircraft satellite/ground phone number of all participants
Daily coordination email sent to all pilots on email list from each ops organization regarding planned flights (list serve)
Science leads to inform flight crew of other aircraft plans during flights
Dropsondes will be coordinated with ARTCC but the responsibility for dropsondes launches lies with the PIC
Dropsonde mission rule complete

## Slide 84: Aviation Safety
A flight plan will be filed with the FAA for all flights per the COA
Flight on the programmed Mission plan (black line) shall be utilized except where flight safety or science mission interests dictate a need to alter the flt path
  Such changes will be made in accordance with the COA
  Experience is that ‘go to’ diverts were flown 80% of the time
Pilot situational awareness will be enhanced with systems installed on the a/c and used during GRIP
  Low-light nose camera image display (updated for AV6)
  Storm scope display
  GHIS II accelerometer

## Slide 85: GH SHOUT Mission Confirmation of Notification Sheet Green – Rec’d response (Conf. of Notification), via email or Dip Note Bold Black – Post Receipt of Action Request

## Slide 86: GH SHOUT Mission Confirmation of Notification Sheet
Dominican Republic | 
Ecuador | 6/26/15
El Salvador | 6/18/15
French Guiana - FR | 
Grenada | 6/15/15 – via Dip Note 26
Guadeloupe - FR | 
Guatemala | 6/22/15 - via Authorization Docs.
Guyana | 7/1/15
Haiti – State CDO POC | 
Honduras | 7/8/15 – via Dip Note 217
Jamaica | 7/9/15
Martinique - FR | 
Mexico | 
Montserrat - UK | 6/12/15
The Netherlands | 6/16/15
Nicaragua | 6/23/15 – via Dip Note 231/2015
Panama | 6/16/15 – clearance # TA5082
Saint Barthelemy - FR | 
Saint Kitts & Nevis - EB | 
Saint Lucia - EB | 

## Slide 87: GH SHOUT Mission Confirmation of Notification Sheet
Saint Martin - FR | 
Saint Pierre & Miquelon - FR | 
Saint Vincent & The Grenadines - EB | 
Sint Maarten | 6/16/15
Suriname | 6/9/15- via Dip Note 083/15
Trinidad & Tobago | 7/1/15
Turks and Caicos - UK | 6/12/15
Cape Verde | 6/23/15
Cote D'Ivoire – Africa – State CDO POC | 
The Gambia – Africa – State CDO POC | 
Guinea-Bissau – Africa – State CDO POC | 
Mauritania | 6/29/15
Senegal – Africa – State CDO POC | 
Canary Islands - Spain | 6/16/15 – via Dip Note 470
Madeira Islands - Portugal | 6/9/15 – via Dip Note 134-15
Azores - Portugal | 6/9/15 – via Dip Note 134-15
Kiribati | 7/11/15
Tahiti- FR | 
Pitcairn Islands - UK | 6/12/15
Western Sahara – Africa – State CDO POC | 

## Slide 89: Integration Status for AV-6
Global Hawk hangar and experimenter work area.

## Slide 90: SHOUT WFF/AFRC KU SAT Update
GHOC-E, KU are operational

## Slide 91
Wallops Facilities Status
Ron Walsh

## Slide 92: SHOUT Deployment Status to WFF
• Facility
- lab
- phone and IT infrastructure
- trailer power and IT
• Chase plane
• Full support
• Documentation & Reviews

## Slide 93
WFF Aircraft Office – Mission Readiness
G |  | WFF Weather Office & Meteorologists |  | 
G |  | WFF Airport & Airport Tower Controllers |  | 
G |  | WFF SureTrak radar display in GHMOF |  | 
G |  | WFF video and photo coverage |  | 
G |  | WFF IT & phone infrastructure |  | 
G |  | WFF Portable Trunk Radios |  | 
G |  | WFF commercial power & diesel backup |  | 
Y |  | WFF Chase aircraft |  | 
 |  | Y |  | T-34C (primary) [arrival scheduled for 8/27 1200 EDT]
 |  | G |  | King Air (backup)
 |  | G |  | Air Crew
 |  | Y |  | Chase Practice Flight with a simulated GH
Y |  | WFF Safety |  | 
 |  | G |  | Final flight routes from Dryden (transit and science)
 |  | Y |  | GH Emitter info from Dryden for HERP & Spectrum Mgmt
 |  | 8/27 |  | WFF Ground Safety Plan (GSP) [95% complete]
 |  | 8/27 |  | WFF Flight Safety Plan (FSP) [95% complete]
G |  | WFF Security |  | 
 |  | G |  | WFF Visitor Badging (complete through 8/30 arrivals)
 |  | G |  | Distributed building keys for N-159 after hours access
8/27 |  | WFF Mission Operations Directive (MOD) [in signature loop] |  | 
Y |  | WFF Special Use Airspace (SUA) |  | 
 |  | G |  | NASA R-6604
 |  | G |  | VACAPES above 45,000'
 |  | Y |  | VACAPES Test Track "C" (LOA with VACAPES/PAX/DFRC/WFF)
8/28 |  | WFF Authority to Proceed with HS3 Flight Operations |  | 

## Slide 94
d
Hangar D-1 1st Floor
N106
S115
Shared
Break Room
AVAPS/LIP
HIWRAP/HAMSR
AV-6
10 Benches
Conference
Room
N104
N110
N108
114
Ground Crew
Shared Office

## Slide 95: Work benches are ready to go under the tail of the P3!
DFRC GH & ESPO Personnel
PI – A/C Network
DFRC Payload & Data Support Personnel

## Slide 96: Safety & Security Issues have been addressed
Orientation Package – complete; distributed
Security – 24/7 access
All Hands briefings - recorded
Badging – FN badging issue in work
Safety equipment in N159
Medical – Health Unit, Hearing protection, insect repellant
Evacuation Plan - complete

## Slide 97: Miscellaneous

## Slide 98: Communications Structure Set up
Mission Information and notifications will be sent to the SHOUT List serve
Daily meeting schedule
WebEx/Telecon for most meetings
Local contact info for all team members as back up to poor cell service
Brick radios can be checked out during mission for critical personnel
A daily plan of the day will be:
  posted on the SHOUT website & emailed to the SHOUT list serve
  On the WFF Operations Schedule Recording 757-824-1176#2?????
Mission Tool Suite

## Slide 99: Mission Tools has been upgraded and is being used for the dry run and CST JD UPDATING
Flight reports/science reports
Instructions and Documentation (i.e. Flt Planning A/C Summary)
Tools & links
Schedules & Shift summaries

## Slide 100: SHOUT Public Affairs, Education, Outreach
Limited Media/Public Affairs
Visitor Day (VIP)
AUVSI Visit

## Slide 101: In Summary
• Reviews: ORR complete
Tech Reviews 8/3/15
Lessons Learned 8/4/15
• Instruments – Status
• Aircraft – no major issues
• Facilities – WFF delays due to funding delay
• Coordination with other agencies - ready
• Documentation:
Minor
WWF Frequency clearances - pending
LOA NASA, VACAPES & PAX River – pending
Transit Delay
Range Flight -
Hangar Fire Waiver – pending
COA - pending
RTF – pending
WFF – ATP ACTIONS
Requesting ATP