(DRAFT) CRUISE  INSTRUCTIONS

NOAA Ship RONALD H. BROWN

April 23, 2002

| Cruise Number: | RB-02-04 |
| --- | --- |
| Project: | Western Boundary Climate Time-Series |
| Cruise dates: | 17-30 June 2002 |
| Chief Scientist: | Sonia Bauer, NOAA/AOML |
| Working Area: | Atlantic Ocean, Florida Straits & East of the Bahamas |
| Itinerary: | Depart: Jacksonville, FL - 17 Jun. |
|  | Arrive: Miami, FL - 30 Jun. |

Endorsements:

_____________________

Molly Baringer

Scientific Cruise Coordinator

NOAA/AOML

_____________________	______________________		_______________________

Sonia Bauer			Dr. Kristina Katsaros			RADM Nick Prahl

Chief Scientist			Director, AOML			Director, MOC

NOAA/AOML			Miami, FL 33133			Norfolk, VA 23510

CRUISE OVERVIEW

A.  Summary

The Abaco time series began in earnest in August 1984 when NOAA extended its Straits of Florida program to include measurements of western boundary current transports and watermass properties east of Abaco, the Bahamas. Since 1986, over 20 hydrographic sections have been completed east of Abaco, most including direct velocity observations by Pegasus and/or Lowered Acoustic Doppler Current Profiler (LADCP). Transient tracer (CFC) measurements have been made on 7 of these sections, at roughly 2-year intervals. Current meter arrays have been maintained nearly continuously since April, 1986.

The repeated hydrographic and tracer sampling at Abaco has established a high-resolution record of watermass properties in the Deep Water Boundary Current (DWBC) at 26N, which for temperature and salinity can be reasonably constructed back to about 1955 (Vaughan and Molinari, 1997; Molinari et al.,1998). Events such as the intense convection period in the Labrador Sea and renewal of classical Labrador Sea Water in the 1980's are clearly reflected in the cooling and freshening of the DWBC waters off Abaco, and the arrival of a strong CFC pulse, approximately 10 years later.  This array is unique in that it is not just a single time series site but a transport section, of which very few are available in the ocean that approach a decade in length.

To achieve the goals of NOAA's strategic plan in terms of understanding the Atlantic Ocean's role in decadal and longer time scale climate variability, these continued time series observations at Abaco are seen as serving three main purposes:

1. Monitoring of the DWBC for watermass and transport signatures related to changes in the strengths and regions of high latitude water mass formation in the North Atlantic.  Monitoring watermass properties in the DWBC at key locations is one part of an effort to track decadal changes in large-scale watermass properties.

2. Serving as a western boundary endpoint of a subtropical Meridional Overturning Circulation (MOC)/heat flux monitoring system designed to measure the interior dynamic height difference across the Atlantic basin and the associated baroclinic heat transport.

3. Monitoring the intensity of the Antilles current as an index (together with the Florida Current) of inter-annual variability in the strength of the subtropical gyre.  Variations in the strength of the subtropical gyre in relation to the North Atlantic Oscillation (NAO) has been proposed as an important mechanism in the atmosphere-ocean feedback within coupled models (e.g., Latif and Barnett, 1996).

During the June 2002 survey, full water column hydrographic and CTD observations are to be taken in the Florida Straits and East of Abaco Island, Bahamas.  Inverted Echo Sounder mooring stations will be observed, and recovery will commence only if problems are indicated.

B.  Operating Area

The operating area is in the Straits of Florida and East of Abaco, Bahamas at 26N.  See Figure 1.

Figure 1: Station locations for the Western Boundary Climate Time-Series.

C.  Participating Institutions

United States Department of CommerceNational Oceanic and Atmospheric Administration Atlantic Oceanographic and Meteorological Laboratory (NOAA/AOML)Physical Oceanography Division 4301 Rickenbacker Causeway Miami, FL 33149 USA Telephone: 001 305 361 4430 Facsimile: 001 305 361 4392

University of Miami

Rosenstiel School for Marine and Atmospheric Science (RSMAS)

4600 Rickenbacker Causeway

Miami, FL 33149

D. Personnel

Name				Sex		Nationality		Affiliation

Sonia Bauer		 	F		USA			NOAA/AOML

Robert Roddy			M		USA			NOAA/AOML

Douglas Anderson		M		USA			NOAA/AOML

Ryan Smith			M		USA			NOAA/AOML

Technician			M		USA			NOAA/AOML

Michael Meltzer		M		USA			CTD watch stander

*Marie O’Brien		F		USA			CTD watch Stander

Mate 1				?		?			not yet confirmed

Mate 2				?		?			not yet confirmed

* The chief scientist assumes responsibility for this minor.  Her parents have approved the chief scientist acting as guardian while on the cruise and have approved appropriate medical treatment as deemed necessary and have indicated this on the individual’s health questionnaire.

E.  Administrative

Chief Scientist:		Dr. Sonia Bauer

Atlantic Oceanographic and Meteorological Laboratory

4301 Rickenbacker Causeway Miami, FL 33149 USA

Telephone: 305-361-4430 Facsimile: 305-361-4412

Sonia.Bauer@noaa.gov

Co-Chief Scientist:		Dr. Molly Baringer

Atlantic Oceanographic and Meteorological Laboratory

4301 Rickenbacker Causeway Miami, FL 33149 USA

Telephone: 305-361-4345  Facsimile: 305-361-4412

Molly.Baringer@noaa.gov

Alternate Point of Contact:	LT Joseph A. Pica

Atlantic Oceanographic and Meteorological Laboratory

4301 Rickenbacker Causeway Miami, FL 33149 USA

Telephone: 305-361-4544 Facsimile: 305-361-4449

Joseph.A.Pica@noaa.gov

Clearances:	Research clearance is being requested through the Marine Operations Center, Atlantic, for the Bahamas.

OPERATIONS

A.  Data to be Collected

.	Seabird 911+ CTD to sample profiles of depth along hydrographic transects in the Florida Straits and East of Abaco Island, Bahamas.  Approximately 58 stations will be completed to full water depth, estimated maximum near 6000 meters.

.	General Oceanics 24 bottle rosette wheel to collect water samples for comparison with the CTD profiles.

.	RDI 150kHz Lowered Acoustic Doppler Current Profiler (LADCP) to measure profiles of northward and eastward velocity.

.	One salinometer Guideline model 8400 to measure the salinity of the water samples collected with the bottles.

.	One automated oxygen titration system built by NOAA to measure the dissolved oxygen concentration in the water samples.

.	Continuous recording of ship mounted ADCP data.

.	Continuous recording of Thermosalinograph (TSG).

Continuous recording of Seabeam bathymetry requested (with help from ship science technician)

Need 12 kHz acoustic tracking of CTD package to within 10 meters of the bottom (LSR/PDR).

Need Line Scan Recorder and PDR working to interface with IES instruments.

B.  Staging Plan

Staging for the cruise will be conducted in Jacksonville, FL.   A list of the equipment to be brought aboard is shown in the FACILITIES section of the Project Instructions and in Appendix B.

C.  Cruise Plan

The NOAA Ship Ronald H. Brown (RHB) will depart Jacksonville, FL , on 17 June 2002, to begin scientific operations.  The primary goal of the cruise is to sample along previously occupied hydrographic sections.   All attempts will be made to reoccupy these stations as closely as possible however, prevailing weather conditions as well as changes in scheduling and scientific objectives make the exact determination of the station coordinates impossible at this time.  The actual hydrographic stations sampling plan may deviate from this proposed plan in both number of stations and their locations.  A map of the proposed cruise track is shown in figure 1.  On 30 June 2002, RHB will dock in Miami, FL.

D.  Waypoints

Approximate Station Locations are listed in Table 1.  These are preliminary and subject to change.

Table 1.     Preliminary Station Locations

| Sta |  | lat |  |
| --- | --- | --- | --- |
| long |  | dist | dist | Cum | depth | sta. | Extra | Arrival | Departure |
| # |  |
|  |  | (nm) | (km) | (km) | (m) | time | time | Time | Time |
| 17-Jun 14:00 |
| Sea Buoy | 30 | 24 | N | 81 | 22 | W | 0 | 0 | 0 | 0 | 0 | 0.00 | 17-Jun 16:00 | 17-Jun 16:00 |
| 1 | 26 | 30 | N | 69 | 26 | W | 671.2 | 1243.2 | 1243 | 5600 | 3.8 | 0.10 | 19-Jun 23:55 | 20-Jun 3:49 |
| 2 | 26 | 30 | N | 69 | 50 | W | 21.5 | 39.8 | 1283 | 5600 | 3.8 | 0.10 | 20-Jun 5:37 | 20-Jun 9:31 |
| 3 | 26 | 30 | N | 70 | 14 | W | 21.5 | 39.8 | 1323 | 5600 | 3.8 | 0.10 | 20-Jun 11:40 | 20-Jun 15:34 |
| 4 | 26 | 30 | N | 70 | 41 | W | 24.2 | 44.8 | 1368 | 5600 | 3.8 | 0.80 | 20-Jun 17:59 | 20-Jun 22:35 |
| 5 | 26 | 30 | N | 71 | 0 | W | 17.0 | 31.5 | 1399 | 5432 | 3.8 | 0.15 | 21-Jun 0:17 | 21-Jun 4:14 |
| 6 | 26 | 30 | N | 71 | 21 | W | 18.8 | 34.8 | 1434 | 5429 | 3.8 | 0.15 | 21-Jun 6:06 | 21-Jun 10:03 |
| 7 | 26 | 30 | N | 71 | 44 | W | 20.6 | 38.1 | 1472 | 5333 | 3.8 | 0.15 | 21-Jun 12:07 | 21-Jun 16:04 |
| 8 | 26 | 30 | N | 72 | 6 | W | 19.7 | 36.5 | 1508 | 5229 | 3.8 | 0.15 | 21-Jun 18:02 | 21-Jun 21:59 |
| 9 | 26 | 30 | N | 72 | 28 | W | 19.7 | 36.5 | 1545 | 5110 | 3.5 | 0.15 | 21-Jun 23:57 | 22-Jun 3:36 |
| 10 | 26 | 30 | N | 72 | 51 | W | 20.6 | 38.1 | 1583 | 5088 | 3.5 | 0.15 | 22-Jun 5:40 | 22-Jun 9:19 |
| 11 | 26 | 30 | N | 73 | 13 | W | 19.7 | 36.5 | 1620 | 5019 | 3.5 | 0.15 | 22-Jun 11:17 | 22-Jun 14:56 |
| 12 | 26 | 30 | N | 73 | 35 | W | 19.7 | 36.5 | 1656 | 4890 | 3.5 | 0.15 | 22-Jun 16:54 | 22-Jun 20:33 |
| 13 | 26 | 30 | N | 73 | 58 | W | 20.6 | 38.1 | 1694 | 4630 | 3.3 | 0.15 | 22-Jun 22:36 | 23-Jun 2:03 |
| 14 | 26 | 30 | N | 74 | 15 | W | 15.2 | 28.2 | 1722 | 4521 | 3.2 | 0.15 | 23-Jun 3:35 | 23-Jun 6:56 |
| 15 | 26 | 30 | N | 74 | 31 | W | 14.3 | 26.5 | 1749 | 4527 | 3.2 | 0.15 | 23-Jun 8:22 | 23-Jun 11:43 |
| 16 | 26 | 30 | N | 74 | 48 | W | 15.2 | 28.2 | 1777 | 4506 | 3.2 | 0.15 | 23-Jun 13:14 | 23-Jun 16:35 |
| 17 | 26 | 30 | N | 75 | 5 | W | 15.2 | 28.2 | 1805 | 4595 | 3.2 | 0.15 | 23-Jun 18:06 | 23-Jun 21:27 |
| 18 | 26 | 30 | N | 75 | 18 | W | 11.6 | 21.6 | 1827 | 4604 | 3.2 | 0.15 | 23-Jun 22:37 | 24-Jun 1:58 |
| 19 | 26 | 30 | N | 75 | 30 | W | 10.7 | 19.9 | 1847 | 4652 | 3.2 | 0.15 | 24-Jun 3:02 | 24-Jun 6:23 |
| 20 | 26 | 30 | N | 75 | 42 | W | 10.7 | 19.9 | 1867 | 4658 | 3.2 | 0.80 | 24-Jun 7:28 | 24-Jun 11:28 |
| 21 | 26 | 30 | N | 75 | 54 | W | 10.7 | 19.9 | 1886 | 4710 | 3.2 | 0.15 | 24-Jun 12:32 | 24-Jun 15:53 |
| 22 | 26 | 30 | N | 76 | 5 | W | 9.8 | 18.2 | 1905 | 4763 | 3.3 | 0.15 | 24-Jun 16:52 | 24-Jun 20:19 |
| 23 | 26 | 30 | N | 76 | 12 | W | 6.3 | 11.6 | 1916 | 4780 | 3.3 | 0.15 | 24-Jun 20:57 | 25-Jun 0:24 |
| 24 | 26 | 30 | N | 76 | 18 | W | 5.4 | 9.9 | 1926 | 4795 | 3.3 | 0.15 | 25-Jun 0:56 | 25-Jun 4:23 |
| 25 | 26 | 30 | N | 76 | 25 | W | 6.3 | 11.6 | 1938 | 4808 | 3.3 | 0.15 | 25-Jun 5:01 | 25-Jun 8:28 |
| 26 | 26 | 30 | N | 76 | 29 | W | 3.6 | 6.6 | 1944 | 4808 | 3.3 | 0.80 | 25-Jun 8:49 | 25-Jun 12:55 |
| 27 | 26 | 30 | N | 76 | 32.5 | W | 3.1 | 5.8 | 1950 | 4808 | 3.3 | 0.15 | 25-Jun 13:14 | 25-Jun 16:41 |
| 28 | 26 | 30 | N | 76 | 36 | W | 3.1 | 5.8 | 1956 | 4469 | 3.2 | 0.15 | 25-Jun 17:00 | 25-Jun 20:21 |
| 29 | 26 | 30 | N | 76 | 39.5 | W | 3.1 | 5.8 | 1962 | 4460 | 3.2 | 0.15 | 25-Jun 20:40 | 26-Jun 0:01 |
| 30 | 26 | 30 | N | 76 | 43 | W | 3.1 | 5.8 | 1968 | 3797 | 3.2 | 0.15 | 26-Jun 0:19 | 26-Jun 3:40 |
| 31 | 26 | 30 | N | 76 | 46.5 | W | 3.1 | 5.8 | 1973 | 1382 | 1.5 | 0.15 | 26-Jun 3:59 | 26-Jun 5:38 |
| 32 | 26 | 31 | N | 76 | 50 | W | 3.3 | 6.1 | 1980 | 1000 | 4 | 0.80 | 26-Jun 5:58 | 26-Jun 10:46 |
| 33 | 26 | 31 | N | 76 | 54 | W | 3.6 | 6.6 | 1986 | 709 | 0.8 | 0.15 | 26-Jun 11:07 | 26-Jun 12:04 |
| Waypoint | 25 | 48 | N | 77 | 11 | W | 45.6 | 84.5 | 2071 | 0 | 0.0 | 0.00 | 26-Jun 15:52 | 26-Jun 15:52 |
| 34 | 26 | 26 | N | 78 | 40 | W | 88.5 | 163.9 | 2150 | 750 | 0.8 | 0.15 | 26-Jun 23:15 | 27-Jun 0:12 |
| 35 | 26 | 20 | N | 78 | 43 | W | 6.6 | 12.2 | 2162 | 700 | 0.8 | 0.15 | 27-Jun 0:51 | 27-Jun 1:48 |
| 36 | 26 | 15 | N | 78 | 46 | W | 5.7 | 10.5 | 2173 | 500 | 0.5 | 0.15 | 27-Jun 2:22 | 27-Jun 3:01 |
| 37 | 26 | 10 | N | 78 | 48 | W | 5.3 | 9.8 | 2183 | 450 | 0.5 | 0.15 | 27-Jun 3:33 | 27-Jun 4:12 |
| 38 | 26 | 4 | N | 78 | 51 | W | 6.6 | 12.2 | 2195 | 300 | 0.5 | 0.15 | 27-Jun 4:52 | 27-Jun 5:31 |
| Waypoint | 26 | 30 | N | 78 | 56 | W | 26.4 | 48.9 | 2244 | 0 | 0.0 | 0.00 | 27-Jun 7:43 | 27-Jun 7:43 |
| 39 | 27 | 0 | N | 79 | 12 | W | 33.2 | 61.6 | 2305 | 470 | 1 | 0.15 | 27-Jun 10:29 | 27-Jun 11:38 |
| 40 | 27 | 0 | N | 79 | 17 | W | 4.5 | 8.3 | 2313 | 607 | 1 | 0.15 | 27-Jun 12:05 | 27-Jun 13:14 |
| 41 | 27 | 0 | N | 79 | 23 | W | 5.3 | 9.9 | 2323 | 681 | 1 | 0.15 | 27-Jun 13:46 | 27-Jun 14:55 |
| 42 | 27 | 0 | N | 79 | 30 | W | 6.2 | 11.6 | 2335 | 760 | 1 | 0.15 | 27-Jun 15:32 | 27-Jun 16:41 |
| 43 | 27 | 0 | N | 79 | 37 | W | 6.2 | 11.6 | 2346 | 661 | 1 | 0.15 | 27-Jun 17:18 | 27-Jun 18:27 |
| 44 | 27 | 0 | N | 79 | 41 | W | 3.6 | 6.6 | 2353 | 540 | 1 | 0.15 | 27-Jun 18:49 | 27-Jun 19:58 |
| 45 | 27 | 0 | N | 79 | 47 | W | 5.3 | 9.9 | 2363 | 377 | 1 | 0.15 | 27-Jun 20:30 | 27-Jun 21:39 |
| 46 | 27 | 0 | N | 79 | 52 | W | 4.5 | 8.3 | 2371 | 273 | 1 | 0.15 | 27-Jun 22:06 | 27-Jun 23:15 |
| 47 | 27 | 0 | N | 79 | 56 | W | 3.6 | 6.6 | 2378 | 141 | 1 | 0.15 | 27-Jun 23:36 | 28-Jun 0:45 |
| 48 | 26 | 3 | N | 79 | 14 | W | 68.3 | 126.5 | 2504 | 175 | 1 | 0.15 | 28-Jun 7:35 | 28-Jun 8:44 |
| 49 | 26 | 3 | N | 79 | 18.8 | W | 4.3 | 8.0 | 2512 | 145 | 1 | 0.15 | 28-Jun 9:10 | 28-Jun 10:19 |
| 50 | 26 | 3 | N | 79 | 23.9 | W | 4.6 | 8.6 | 2521 | 125 | 1 | 0.15 | 28-Jun 10:46 | 28-Jun 11:55 |
| 51 | 26 | 3 | N | 79 | 28.9 | W | 4.4 | 8.2 | 2529 | 125 | 1 | 0.15 | 28-Jun 12:22 | 28-Jun 13:31 |
| 52 | 26 | 3 | N | 79 | 34 | W | 4.6 | 8.6 | 2538 | 150 | 1 | 0.15 | 28-Jun 13:59 | 28-Jun 15:08 |
| 53 | 26 | 3 | N | 79 | 39.9 | W | 5.3 | 9.8 | 2547 | 150 | 1 | 0.15 | 28-Jun 15:39 | 28-Jun 16:48 |
| 54 | 26 | 3 | N | 79 | 46 | W | 5.4 | 10.1 | 2558 | 145 | 1 | 0.15 | 28-Jun 17:21 | 28-Jun 18:30 |
| 55 | 26 | 3 | N | 79 | 51 | W | 4.5 | 8.4 | 2566 | 125 | 1 | 0.15 | 28-Jun 18:57 | 28-Jun 20:06 |
| 56 | 26 | 3 | N | 79 | 56 | W | 4.5 | 8.3 | 2574 | 130 | 1 | 0.15 | 28-Jun 20:33 | 28-Jun 21:42 |
| 57 | 26 | 3 | N | 79 | 59.9 | W | 3.6 | 6.6 | 2581 | 130 | 1 | 0.15 | 28-Jun 22:03 | 28-Jun 23:12 |
| 58 | 26 | 3 | N | 80 | 3.9 | W | 3.6 | 6.6 | 2587 | 140 | 1 | 0.15 | 28-Jun 23:34 | 29-Jun 0:43 |
| Sea Buoy | 25 | 46 | N | 80 | 5 | W | 17.0 | 31.5 | 2619 | 0 |  |  | 29-Jun 2:25 | 29-Jun 2:25 |

Table 1 (continued).     Preliminary Station Locations

E.  Station Operations

CTD Operations:  CTD casts will include the CTD unit, a Lowered ADCP unit and a Rosette sampler.  Approximately 58 casts will be conducted to full water column depth, maximum estimated at 6000 meters.

IES Mooring Evaluations: While the CTD is in the water at the IES locations, a acoustic device will be lowered into the water to communicate with the acoustic releases of the IES moorings to check on their status.  We require the use of the ships Line Scan Recorder and PDR to receive communications from the IESs.  Mooring recovery and deployments are not planned for this cruise, although recovery might occur if problems are encountered.  Recovery and redeployment of these moorings are scheduled for late November, early December, 2002 (tentatively on the R/V Ronald H. Brown)..

F.  Underway Operations

The ship shall continuously collect P-code GPS, ADCP, meteorological, thermosalinograph (TSG), and bathymetric (Seabeam) data while underway.

G.  Small Boat Operations

Small boat operations are not anticipated to be needed for this cruise.

H.  De-staging Plan

De-staging will occur on 30 June 2002, while the ship is in Miami, FL

FACILITIES

A.  Equipment and Capabilities Provided by the Ship

The following communications devices are currently on board the Ronald H. Brown.

High Frequency SSB (SEA 330):  SEA Inc. 300-watt high frequency transceiver. The transceiver covers a frequency range from 1.6 to 29.9 MHz

Sperry Global Maritime Distress and Safety System (GMDSS)

Satellite communication system (INMARSAT -A, -B, -M).

Five fixed VHF radios with eight channels pre programmed with a selection of marine band and NOAA frequencies.

Cell phones

The electronic instrumentation used for navigation includes:

Trimble Centurion P-code GPS

Magnavox MX-200 GPS

Northstar 941x differential GPS

Sperry Mark 37 Gyro Compass

Sperry Rascar Touch Screen navigational radar. (S-band (10 cm) 30 kW radar and an X-band (3 cm) 25 kW radar)

Simrad Robertson Dynamic Positioning System

Raytheon model DSN-450 Doppler Speed/distance log

NAVTEX receiving and printing the international automated medium frequency (518 KHz) weather warnings

Weather fax: Medium frequency/high frequency

Scientific Equipment requested from the Ship

Echo Sounder (Ocean Data Equipment Corporation (ODEC) Bathy 2000) used in 12 kHz mode (to track CTD package to within 10 meters of the bottom) to be used while on CTD station.

Continuous Seabeam 2112 (12 Khz) swath bathymetric sonar system sampling while underway between stations.

Barometer

WOCE IMET sensors

Hydrographic Winch system and readouts (using 322 conducting cable for CTD operations).

Hull mounted acoustic Doppler current profiler (RD Instruments (RDI), Model VM-150-18HP, 153.6 KHz narrow band acoustic doppler current profiler) with gyro.

Two Guildline model 8400B auto salinometers in temperature controlled room.

Seabird Electronics Model 9/11+ CTD system, 12-position rosette frame and deck unit to be used as backup for Science Party provided equipment, including recently calibrated dual conductivity/temperature sensor pair.

Line Scan recorder and/or PDR to hear and record responses from Interverted Echo Sounder instruments (IESs), operating in 10-12 kHz range.

B.  Equipment and Capabilities Provided by the Scientists

In addition to the suite of oceanographic and meteorological instruments on board the Ronald H. Brown, the science party will bring the following instruments and materials on board:

Seabird 911+ CTD to collect profiles of depth.

General Oceanics 24 bottle rosette wheel to collect water samples for comparison with the CTD profiles.

RDI 150kHz lowered acoustic Doppler current profiler to measure profiles of northward and eastward velocity.

Salinity sample bottles to augment ship’s supply, including supply of standard sea water.

One automated oxygen titration system built by NOAA to measure the dissolved oxygen concentration in the water samples.

Several computers for data acquisition and initial processing.

Equipment in support IES mooring evaluation.

DISPOSITION OF DATA AND REPORTS

A. Data Responsibilities

The Chief Scientist will be responsible for the disposition, feedback on data quality, and archiving of data and specimens collected on board the ship for the primary project.  As representative of the program manager (Director, AOML), the Chief Scientist will also be responsible for the dissemination of copies of these data to participants in the cruise, to any other requesters, and to NESDIS in accordance with NDM 16-11 (ROSCOP within 3 months of cruise completion). The ship may assist in copying data and reports insofar as facilities allow.

The Chief Scientist will receive all original data gathered by the ship for the primary project, and this data transfer will be documented on NOAA Form 61-29 "Letter Transmitting Data". The Chief Scientist in turn will furnish the ship a complete inventory listing all data gathered by the scientific party detailing types and quantities of data.

Individuals in charge of piggyback projects conducted during the cruise have the same responsibilities for their project's data as the Chief Scientist has for primary project data. All requests for data should be made through the Chief Scientist.

The Commanding Officer is responsible for all data collected for ancillary projects until those data have been transferred to the project's principal investigators or their designees. Data transfers will be documented on NOAA Form 61-29. Copies of ancillary project data will be provided to the Chief Scientist when requested. Reporting and sending copies of ancillary project data to NESDIS (ROSCOP) is the responsibility of the program office sponsoring those projects.

DATA REQUIREMENTS

The ship's SCS system should log the following parameters:

PCODE_TIME (HHMMSS)

PCODE_LAT (DEGMIN)

PCODE_LON (DEGMIN)

PCODE_QUALITY (1=std)

PCODE_COG (Degrees)

PCODE_SOG (Knots)

LRing-Gyro (Degrees)

PCODE-SOG-msec (M/SEC)

TSG_Unit_Temp (Degrees_C)

TSG_Conductivity (Mega_Mhos)

TSG_Salinity (PPT)

Barometer (MB)

Precip9-trwlhs (mm/hr)

Imet-Rain (mm)

Imet-Rel_Hum (Percent)

Imet-Temp (Degrees_C)

Fluoro-Value (PPM)

Imet-TWind1-Speed-MSEC (M/SEC)

Imet-Twind1-Dir (Degrees)

Imet-Rwind2-Spd-Knts (Knots)

Imet-TWind2-Speed-KNTS (Knots)

Imet-TWind2-Dir (Degrees)

Bottom Depth (meters)

The Survey Department will translate the data from thermosalinograph to ASCII and plot the data on a daily basis.

The ship shall record ADCP raw data continuously during the cruise.

The following data products will be produced by the ship and, if requested, will be given to the Chief Scientist at the end of each leg:

a.navigational log sheets (MOAs);

b.salinity determinations;

c.calibration data for Autosals;

d.copy of SEAS data diskettes;

e.8-mm magnetic tapes of Sea Beam and navigational data, including location and depths of acoustic profile locations;

f. SCS tapes;

g. ADCP raw data on CD

B. Pre- and Post-Cruise Meetings

A pre-cruise meeting between the Commanding Officer and the Chief Scientist will be conducted either the day before or the day of departure, with the express purpose of identifying day-to-day project requirements, in order to best use shipboard resources and identify overtime needs. A brief post-cruise meeting will be held when convenient.

C. Ship Operations Evaluation Report

A Ship Operations Evaluation Report will be completed by the Chief Scientist and given to the Director, AOML, for review and then forwarded to OMAO.

ADDITIONAL PROJECTS

A.  MOC Directives

Any additional work will be subordinate to the primary project and will be accomplished only with the concurrence of the Commanding Officer and the Chief Scientist(s).

The following projects will be conducted by ship's personnel in accordance with the general instructions contained in the MOC Directives, and conducted on a not-to-interfere basis with the primary project:

a.SEAS Data Collection and Transmission

b.Marine Mammal Reporting

c.Bathymetric Trackline

d.Weather Forecast Monitoring

e.Sea Turtle Observations

f.Automated Sounding Aerological Program

B.  Underway Measurements in support of Global Carbon Cycle Research

The underway sensors on RHB will be used in support of the objectives of the Global Carbon Cycle Research (GCC) to quantify the uptake of carbon by the world's ocean and to understand the bio-geochemical mechanisms responsible for variations of partial pressure of CO2 in surface water (pCO2).   This work is a collaborative effort between the CO2 groups at AOML and PMEL.

Principal investigators:

Dr Rik Wanninkhof, AOML 305-361-4379    wanninkhof@aoml.noaa.gov

Dr Richard Feely, PMEL  206-526-6214    feely@pmel.noaa.gov

The semi-automated instruments are installed on a permanent basis in the hydrolab of RHB.   All work is performed on a not-to-interfere basis and does not introduce any added ship logistic requirements other than the continuous operation of the bow water pump and thermosalinograph.  The chief scientist assumes responsibility of the hazardous materials aboard RHB for this project.  A list of the HAZMAT associated with this project are listed in Appendix A.

HAZARDOUS MATERIALS

A. Policy Compliance

RONALD H. BROWN will operate in full compliance with all environmental compliance requirements imposed by NOAA.  All hazardous materials and substances needed to carry out the objectives of the embarked science mission, including ancillary tasks, are the direct responsibility of the embarked designated Chief Scientist, whether or not that Chief Scientist is using them directly.  The ship's Environmental Compliance Officer (ECO) will work with the Chief Scientist to ensure that this management policy is properly executed, and that any problems are brought promptly to the attention of the Commanding Officer.  Scientific HAZMATS will not be left aboard without a trained spill responder from the science party remaining aboard with them.

The scientific party, under supervision of the Chief Scientist, shall be prepared to respond fully to emergencies involving spills of any mission HAZMAT.  This includes providing properly-trained personnel for response, as well as the necessary neutralizing chemicals and clean-up materials.  Ship's personnel are not first responders and will act in a support role only in the event of a spill.

The Chief Scientist is directly responsible for the handling, both administrative and physical, of all scientific party hazardous wastes.  No liquid wastes shall be introduced into the ship's drainage system.  No solid waste material shall be placed in the ship's garbage.

B. Inventory

The Chief Scientist will provide the Commanding Officer with an inventory indicating the amount, concentrations, and intended storage area of each hazardous material brought onboard, and for which the Chief Scientist is responsible (see Appendix A).  This inventory shall be updated at departure, accounting for the amount of material being removed, as well as the amount in science operations and the amount being removed in the form of waste.

The ship's dedicated HAZMAT Locker contains two 45-gallon capacity flammable storage cabinets and one 22-gallon capacity flammable storage cabinet.  Unless there are dedicated storage lockers (meeting OSHA/NFPA standards) in each van, all HAZMAT, except small amounts for ready use, must be stored in the HAZMAT Locker.

C. MSDS

All hazardous materials require a Material Safety Data Sheet (MSDS).  Copies of all MSDSs shall be delivered to the ship at least two weeks prior to sailing.  The Chief Scientist shall have copies of each MSDS available when the hazardous materials are loaded aboard.  Hazardous material for which the MSDS is not provided will not be loaded aboard.

RADIOACTIVE ISOTOPES

No radioactive isotopes will be used on this cruise.

MISCELLANEOUS

A. Scientific Berthing

The Chief Scientist is responsible for assigning berthing for scientific party within the spaces designated as scientific berthing. The ship will send current stateroom diagrams to the Chief Scientist showing authorized berthing spaces. The Chief Scientist is responsible for ensuring the scientific berthing spaces are left in the condition in which they were received; for stripping bedding and linen return; and for the return of any room keys which were issued.

The Chief Scientist is also responsible for the cleanliness of the laboratory spaces and the storage areas utilized by the scientific party, both during the cruise and its conclusion prior to departing the ship.

All persons boarding NOAA vessels give implied consent to comply with all safety and security policies and regulations which are administered by the Commanding Officer.  All spaces and equipment on the vessel are subject to inspection or search at any time.  All personnel must comply with OMAO's Drug and Alcohol Policy dated May 7, 1999 which forbids the possession and/or use of illegal drugs and alcohol aboard NOAA Vessels.

B. Medical Forms and Emergency Contacts

The Chief Scientist will provide medical forms for all cruise participants as soon as practicable and no less than four weeks prior to departure. Forms must be provided to the ship's medical officer.

Prior to departure, the Chief Scientist must provide a listing of emergency contacts to the Executive Officer for all members of the scientific party, with the following information: name, address, relationship to member, and telephone number.

C. Shipboard Safety

Wearing open-toed footwear or shoes that do not completely enclose the foot (such as sandals or clogs) outside of private berthing areas is not permitted.  Steel-toed shoes are required to participate in any work dealing with suspended loads, including CTD deployments and recovery.  The ship does not provide steel-toed boots.  Hard hats are also required when working with suspended loads.  Work vests are required when working near open railings and during small boat launch and recovery operations.  Hard hats and work vests will be provided by the ship when required.

D. Communications

The Chief Scientist or designated representative will have access to ship's telecommunications systems on a cost-reimbursable basis.  Where possible, it is requested that direct payment (e.g. by credit card) be used as opposed to after-the-fact reimbursement. Ship's systems include:

1. INMARSAT-B

INMARSAT-B provides high quality voice and fax communications (9600 baud) and high speed data transmission, including FTP.  Cost is $2.60/min for voice and fax; $7.25/min for high speed.  INMARSAT-B is presently only available direct dialed outgoing and is therefore reserved for official business.  All phone numbers are listed in Item 5 of this section.

2. INMARSAT-M

INMARSAT-M (or Mini-M) provides medium quality voice communications.  Cost is $2.15/min.  INMARSAT-M may be charged to credit card or collect.

3. INMARSAT-A

INMARSAT-A provides high quality voice communications as a backup system.  It can also provide fax communications (9600 baud) and high speed data transmission, including FTP.  Cost varies from $2.65/min to $5.60/min for voice and fax depending on vendor and peak vs off-peak rates.  High speed costs $10.80 - $15.60/min.  INMARSAT-A may be charged to credit card or collect.

**Note:  All rates listed are based on direct-dialed business calls to the US.  Collect, or calls charged to credit calls are charged higher rates, subject to additional fees, and may have minimum charges.

4. E-mail

An e-mail account for each embarked scientist will be established by the ship's LET.  The account name will use the person's first and last name as listed in Personnel Section.  The e-mail address for scientists will use the format: firstname.lastname.atsea@rbnems.ronbrown.omao.noaa.gov

Example: sonia.bauer.atsea@rbnems.ronbrown.omao.noaa.gov

Each member of the ship's complement (crew and scientists) will be authorized to send/receive up to 15 KB of data per day ($1.50/day or $45/month) at no cost.  E-mail costs accrued in excess of this amount must be reimbursed by the individual.  At or near the end of each leg, the Commanding Officer will provide the Chief Scientist with a detailed billing statement for all personnel in his party.  Prior to their departure, the chief scientist will be responsible for obtaining reimbursement from any member of the party whose e-mail costs have exceeded the complimentary amount.

5.  Contacts

Important phone numbers, fax numbers and e-mail addresses: (Up-to-date phone numbers can be found on the MOC web site at www.moc.noaa.gov/phone.htm#RB)

RONALD H. BROWN (to call from US)

- INMARSAT-B VOICE:	011-OAC-336-899-620 (approx $2.60/min)

- INMARSAT-B FAX:    	011-OAC-336-899-621

- INMARSAT "M" VOICE:	011-OAC-761-831-360  (approx $2.99/min)

- INMARSAT-A VOICE: 	011-OAC-154-2643 (approx $5.60/min)

- CELLULAR:     		757-635-0678

- OOD CELLULAR:		206-910-3584

NOTE:   For RB-02-03 cruise, the ship will be operating in range of the Atlantic Ocean Satellite (West) with ocean code = 874.

Program contacts

Sonia Bauer      			Sonia.Bauer@noaa.gov  	305-361-4430

Molly Baringer			Molly.Baringer@noaa.gov	305-361-4345

E-mail addresses:

MOP radio room:             		Radio.Room@noaa.gov

Commanding Officer, RHB		CO.Ronald.Brown@noaa.gov

Executive Officer, RHB   		XO.Ronald.Brown@noaa.gov

Field Operations Officer, RHB	FOO.Ronald.Brown@noaa.gov

Medical Officer, RHB                	Medical.Ronald.Brown@noaa.gov

E.  Port Agent Services/Billing

Contractual agreements exist between the port agents and the Commanding Officer for services provided to NOAA Ship RONALD H. BROWN.  The costs for any services arranged through the ship's agents by the scientific program, which are considered to be outside the scope of the agent/ship support agreement, will be the responsibility of that program. Where possible, it is requested that direct payment be arranged between the science party and port agent, as opposed to after-the-fact reimbursement to the ship's accounts.

F.  Wage Marine Working Hours and Rest Periods

The Chief Scientist shall be cognizant of the reduced capability of RONALD H. BROWN's operating crew to support 24-hour mission activities.  Wage marine employees are subject to negotiated work rules contained in the applicable collective bargaining agreement.  Dayworkers' hours of duty are a continuous eight-hour day, beginning no earlier than 0600 and ending no later than 1800.  It is not permissible to separate such an employee's workday into several short work periods with interspersed non-work periods.  Dayworkers called out to work between the hours of 0000 and 0600 are entitled to a rest period of one hour for each such hour worked.  Such rest periods begin at 0800 and will result in such a dayworker being unavailable to support science operations until the rest period has ended.  All wage marine employees are supervised and assigned work only by the Commanding Officer or his/her designee.  The Chief Scientist and the Commanding Officer shall consult regularly to ensure the shipboard resources available to support the science mission are utilized safely, efficiently, and in accordance with the above policies.

APPENDICES

A. List of Hazardous Materials

CHEMICAL REAGENTS USED FOR THE

DETERMINATION OF DISSOLVED OXYGEN IN SEA WATER

NAME OF CHEMICAL	AMOUNT OF CHEMICAL      	COMMENTS

Manganese Chloride		2 Liters, (600gr/Liter)			Solution

Alkaline Sodium Iodide	2 Liters, (320gr. Sodium Hy-		Solution

droxide + 600gr. Sodium Iodide,

in each liter).

Sulfuric Acid			2 Liters, 280ml/liter			Dilute Solution

Sodium Thiosulfate		3 Liters, 10gr/Liter			Very Dilute Solution

3 vials of 10gr. Thiosulfate		Granular Salt

Potassium Iodate		1 Liter, (0.3567gr/Liter) Std.		Very Dilute Solution

Primary Standard

Triton(R) X-100		1 Liter (Polyethylene Glycol		Solution

Octylphenyl Ether)

B. Equipment/Van List

1) AOML General Scientific Equipment	2) AOML CTD Rosette with LADCP (1)

WT:	0.75 ton					WT:	1 ton

SIZE:	Small miscellaneous equipment,		SIZE:	4'L x 4'W x 6'H

tools, & laptops				SITE:	Standard CTD Location

SITE:	Oceanographic Lab

3) AOML IES (4 Potentially Recovered)

WT:	0.8 ton

SIZE:	4’L x 4’W x 5’H (each)

SITE:	Fantail