## Sheet1
Sta | Lat (dec) |  |  | Lon (dec) |  |  | dist | dist | Cum | depth | wire | Extra | Arrival | Departure | steam (h) | ship | total | total |  | DOW | DAS | Extra Time |  | Shallow Speed | 30 | Total bottles | 24 | 1 | Mon
# | [6 empty] | (nm) | (km) | (km) | (m) | time | time |  | Time | from | speed | hours | days | delta days |  |  | speed startup/down | 0.41667 | Decent speed | 60 | Bottle stop time | 0.013889 | 2 | Tues
[15 empty] | last sta | [6 empty] | cast prep/post | 0.33333 | Transition depth | 200 | Bottom approach | 70 | 3 | Wed
[22 empty] | start setup | 0.33333 | Surface soak | 0.033333 | Bottom Speed | 20 | 4 | Thur
[22 empty] | Total Extra Time | 1.0833 |  |  |  |  | 5 | Fri
[28 empty] | 6 | Sat
[14 empty] | 2015-07-22 11:00 | [13 empty] | 7 | Sun
Charleston | 32.8 | 0 | N | -80 | 0 | W | 0 | 0 | 0 | 0 | 0 | 0 | 2015-07-22 11:00 | 2015-07-22 11:00 | 0 | 11 | 0 | 0 |  | Fri
PNE buoy 1 | 20 | 0 | N | -38 | 0 | W | 2366.5309 | 4383.6041 | 4383.6041 | 0 | 0 | 18 | 2015-08-01 07:39 | 2015-08-02 01:39 | 236.6531 | 10 | 254.6531 | 10.6105 | 10.6105 | Wed
PNE buoy 2 | 20.5 | 0 | N | -23 | 0 | W | 844.6108 | 1564.5007 | 5948.1048 | 0 | 0 | 18 | 2015-08-05 06:26 | 2015-08-06 00:26 | 76.7828 | 11 | 349.4359 | 14.5598 | 3.9493 | Thur
PNE buoy 3 | 11.5 | 0 | N | -23 | 0 | W | 540 | 1000.26 | 6948.3648 | 0 | 0 | 18 | 2015-08-08 01:32 | 2015-08-08 19:32 | 49.0909 | 11 | 416.5268 | 17.3553 | 2.7955 | Fri
PNE buoy 4 | 4 | 0 | N | -23 | 0 | W | 450 | 833.55 | 7781.9148 | 0 | 0.2 | 18 | 2015-08-10 12:26 | 2015-08-11 06:38 | 40.9091 | 11 | 475.6359 | 19.8182 | 2.4629 | Wed
Cape Town | -33.93 | 0 | S | 18.46 | 0 | E | 3267.2417 | 6052.0207 | 13833.9355 | 0 | 0 | 0 | 2015-08-21 17:58 | 2015-08-21 17:58 | 251.3263 | 13 | 726.9622 | 30.2901 | 10.4719 | Thur |  | account for +7 hours time change, and +15.4 hours of "weather time"
Cape Town | -33.93 | 0 | S | 18.46 | 0 | E | 0 | 0 | 13833.9355 | 0 | 0 | 38.9 | 2015-08-21 17:58 | 2015-08-23 08:52 | 0 | 11 | 765.8622 | 31.9109 | 1.6208 | Fri | 32.9109 | 435.15
Cape Town | -33.93 | 0 | S | 18.46 | 0 | E | 0 | 0 | 13833.9355 | 0 | 0 | 435.15 | 2015-08-23 08:52 | 2015-09-10 12:01 | 0 | 11 | 1201.0122 | 50.0422 | 18.1313 | Fri | 17.1313
0 | -28.5167 | 0 | S | 14.95 | 0 | E | 371.3146 | 687.7985 | 14521.7339 | 475 | 0.60417 | 0 | 2015-09-11 21:46 | 2015-09-11 22:22 | 33.7559 | 11 | 1235.3722 | 51.4738 | 1.4317 | Wed | Test Cast Position TBA |  |  | 31
1 | -28.5167 | 0 | S | 14.95 | 0 | E | 0 | 0 | 13833.9355 | 185 | 0.43472 | 1.0833 | 2015-09-11 22:22 | 2015-09-11 23:53 | 0 | 11 | 1236.8903 | 51.5371 | 0.063252 | Fri
2 | -28.7167 | 0 | S | 14.4667 | 0 | E | 28.1423 | 52.129 | 13886.0644 | 258 | 0.48361 | 1.0833 | 2015-09-12 02:27 | 2015-09-12 04:01 | 2.5584 | 11 | 1241.0156 | 51.709 | 0.17189 | Sun
3 | -28.8167 | 0 | S | 14.1833 | 0 | E | 16.0678 | 29.7629 | 13915.8273 | 977 | 0.88306 | 1.0833 | 2015-09-12 05:29 | 2015-09-12 07:27 | 1.4607 | 11 | 1244.4427 | 51.8518 | 0.1428 | Sat
4 | -28.9167 | 0 | S | 13.9667 | 0 | E | 12.8659 | 23.8319 | 13939.6592 | 1738 | 1.4725 | 1.0833 | 2015-09-12 08:37 | 2015-09-12 11:10 | 1.1696 | 11 | 1248.1682 | 52.007 | 0.15523 | Sat
5 | -29.0667 | 0 | S | 13.55 | 0 | E | 23.6485 | 43.8049 | 13983.4641 | 2483 | 1.8864 | 1.0833 | 2015-09-12 13:19 | 2015-09-12 16:17 | 2.1499 | 11 | 1253.2878 | 52.2203 | 0.21332 | Sun
6 | -29.2667 | 0 | S | 13.05 | 0 | E | 28.8138 | 53.3728 | 14036.837 | 3144 | 2.2536 | 1.0833 | 2015-09-12 18:54 | 2015-09-12 22:15 | 2.6194 | 11 | 1259.2441 | 52.4685 | 0.24818 | Sun
7 | -29.5 | 0 | S | 12.475 | 0 | E | 33.161 | 61.4252 | 14098.2622 | 3643 | 2.5308 | 1.0833 | 2015-09-13 01:16 | 2015-09-13 04:52 | 3.0146 | 11 | 1265.8729 | 52.7447 | 0.2762 | Mon
8 | -29.7333 | 0 | S | 11.9 | 0 | E | 33.0983 | 61.3091 | 14159.5712 | 3969 | 2.7119 | 1.0833 | 2015-09-13 07:53 | 2015-09-13 11:41 | 3.0089 | 11 | 1272.6771 | 53.0282 | 0.28351 | Mon
9 | -29.75 | 0 | S | 11.325 | 0 | E | 29.9721 | 55.5183 | 14215.0895 | 4156 | 2.8158 | 1.0833 | 2015-09-13 14:24 | 2015-09-13 18:18 | 2.7247 | 11 | 1279.3011 | 53.3042 | 0.276 | Sun | C14
10 | -29.75 | 0 | S | 10.75 | 0 | E | 29.9528 | 55.4826 | 14270.5721 | 4379 | 2.9397 | 1.0833 | 2015-09-13 21:01 | 2015-09-14 01:03 | 2.723 | 11 | 1286.0471 | 53.5853 | 0.28108 | Sun | C14
11 | -29.75 | 0 | S | 10.175 | 0 | E | 29.9528 | 55.4826 | 14326.0548 | 4814 | 3.1814 | 1.0833 | 2015-09-14 03:46 | 2015-09-14 08:02 | 2.723 | 11 | 1293.0348 | 53.8764 | 0.29115 | Sun | C14
12 | -29.75 | 0 | S | 9.6 | 0 | E | 29.9528 | 55.4826 | 14381.5374 | 4909 | 3.2342 | 1.0833 | 2015-09-14 10:45 | 2015-09-14 15:05 | 2.723 | 11 | 1300.0753 | 54.1698 | 0.29335 | Sun
13 | -29.75 | 0 | S | 9.025 | 0 | E | 29.9528 | 55.4826 | 14437.02 | 4990 | 3.2792 | 1.0833 | 2015-09-14 17:48 | 2015-09-14 22:10 | 2.723 | 11 | 1307.1608 | 54.465 | 0.29523 | Sun | Drifter
14 | -29.75 | 0 | S | 8.45 | 0 | E | 29.9528 | 55.4826 | 14492.5026 | 5042 | 3.3081 | 1.0833 | 2015-09-15 00:53 | 2015-09-15 05:17 | 2.723 | 11 | 1314.2751 | 54.7615 | 0.29643 | Sun
15 | -29.75 | 0 | S | 7.875 | 0 | E | 29.9528 | 55.4826 | 14547.9853 | 4932 | 3.2469 | 1.0833 | 2015-09-15 08:00 | 2015-09-15 12:20 | 2.723 | 11 | 1321.3284 | 55.0554 | 0.29389 | Sun
16 | -29.75 | 0 | S | 7.3 | 0 | E | 29.9528 | 55.4826 | 14603.4679 | 5132 | 3.3581 | 1.0833 | 2015-09-15 15:03 | 2015-09-15 19:30 | 2.723 | 11 | 1328.4928 | 55.3539 | 0.29852 | Sun
17 | -29.7333 | 0 | S | 6.725 | 0 | E | 29.9721 | 55.5183 | 14658.9861 | 5071 | 3.3242 | 1.0833 | 2015-09-15 22:13 | 2015-09-16 02:38 | 2.7247 | 11 | 1335.625 | 55.651 | 0.29718 | Sun
18 | -29.75 | 0 | S | 6.15 | 0 | E | 29.9721 | 55.5183 | 14714.5044 | 5045 | 3.3097 | 1.0833 | 2015-09-16 05:21 | 2015-09-16 09:45 | 2.7247 | 11 | 1342.7428 | 55.9476 | 0.29657 | Sun
19 | -29.75 | 0 | S | 5.575 | 0 | E | 29.9528 | 55.4826 | 14769.987 | 5101 | 3.3408 | 1.0833 | 2015-09-16 12:28 | 2015-09-16 16:53 | 2.723 | 11 | 1349.8899 | 56.2454 | 0.2978 | Sun | Drifter | Argo
20 | -29.75 | 0 | S | 5 | 0 | E | 29.9528 | 55.4826 | 14825.4697 | 5094 | 3.3369 | 1.0833 | 2015-09-16 19:37 | 2015-09-17 00:02 | 2.723 | 11 | 1357.0332 | 56.5431 | 0.29764 | Sun
21 | -29.75 | 0 | S | 4.425 | 0 | E | 29.9528 | 55.4826 | 14880.9523 | 5012 | 3.2914 | 1.0833 | 2015-09-17 02:45 | 2015-09-17 07:08 | 2.723 | 11 | 1364.1309 | 56.8388 | 0.29574 | Sun
22 | -29.6333 | 0 | S | 3.85 | 0 | E | 30.7773 | 57.0098 | 14937.9621 | 5006 | 3.2881 | 1.0833 | 2015-09-17 09:56 | 2015-09-17 14:18 | 2.7979 | 11 | 1371.3002 | 57.1375 | 0.29872 | Sun
23 | -29.4667 | 0 | S | 3.3 | 0 | E | 30.398 | 56.3073 | 14994.2694 | 4739 | 3.1397 | 1.0833 | 2015-09-17 17:04 | 2015-09-17 21:17 | 2.7635 | 11 | 1378.2868 | 57.4286 | 0.2911 | Sun
24 | -29.35 | 0 | S | 2.8333 | 0 | E | 25.3787 | 47.0099 | 15041.2793 | 4268 | 2.8781 | 1.0833 | 2015-09-17 23:36 | 2015-09-18 03:33 | 2.3072 | 11 | 1384.5553 | 57.6898 | 0.26119 | Sun | Drifter
25 | -29.3833 | 0 | S | 2.7 | 0 | E | 7.251 | 13.4312 | 15054.7105 | 2841 | 2.0853 | 1.0833 | 2015-09-18 04:13 | 2015-09-18 07:23 | 0.65918 | 11 | 1388.3831 | 57.8493 | 0.15949 | Fri
26 | -29.4 | 0 | S | 2.6167 | 0 | E | 4.4685 | 8.2771 | 15062.9876 | 1936 | 1.5825 | 1.0833 | 2015-09-18 07:47 | 2015-09-18 10:27 | 0.40623 | 11 | 1391.4552 | 57.9773 | 0.128 | Fri
27 | -29.4333 | 0 | S | 2.4333 | 0 | E | 9.7913 | 18.1367 | 15081.1244 | 2808 | 2.0669 | 1.0833 | 2015-09-18 11:21 | 2015-09-18 14:30 | 0.89012 | 11 | 1395.4955 | 58.1456 | 0.16835 | Fri
28 | -29.5333 | 0 | S | 1.9667 | 0 | E | 25.0982 | 46.4902 | 15127.6146 | 2751 | 2.0353 | 1.0833 | 2015-09-18 16:47 | 2015-09-18 19:54 | 2.2817 | 11 | 1400.8958 | 58.3707 | 0.22501 | Sun
29 | -29.6 | 0 | S | 1.6917 | 0 | E | 14.899 | 27.5978 | 15155.2124 | 3655 | 2.5375 | 1.0833 | 2015-09-18 21:15 | 2015-09-19 00:52 | 1.3545 | 11 | 1405.8711 | 58.578 | 0.2073 | Sat
30 | -29.7333 | 0 | S | 1.1167 | 0 | E | 31.0263 | 57.471 | 15212.6834 | 3650 | 2.5347 | 1.0833 | 2015-09-19 03:42 | 2015-09-19 07:19 | 2.8206 | 11 | 1412.3097 | 58.8462 | 0.26828 | Sun
31 | -29.8667 | 0 | S | 0.5417 | 0 | E | 30.9893 | 57.4026 | 15270.086 | 3129 | 2.2453 | 1.0833 | 2015-09-19 10:08 | 2015-09-19 13:27 | 2.8172 | 11 | 1418.4555 | 59.1023 | 0.25608 | Sun
32 | -30 | 0 | S | -0.0333 | 0 | W | 30.9492 | 57.3282 | 15327.4142 | 4085 | 2.7764 | 1.0833 | 2015-09-19 16:16 | 2015-09-19 20:08 | 2.8136 | 11 | 1425.1288 | 59.3804 | 0.27805 | Sun | Drifter | Argo
33 | -30.0167 | 0 | S | -0.4833 | 0 | W | 23.4022 | 43.3486 | 15370.7628 | 4719 | 3.1286 | 1.0833 | 2015-09-19 22:15 | 2015-09-20 02:28 | 2.1275 | 11 | 1431.4682 | 59.6445 | 0.26414 | Sun
34 | -30.0167 | 0 | S | -1.0583 | 0 | W | 29.8728 | 55.3344 | 15426.0972 | 4446 | 2.9769 | 1.0833 | 2015-09-20 05:11 | 2015-09-20 09:15 | 2.7157 | 11 | 1438.2442 | 59.9268 | 0.28233 | Sun
35 | -30 | 0 | S | -1.6333 | 0 | W | 29.8921 | 55.3702 | 15481.4674 | 4673 | 3.1031 | 1.0833 | 2015-09-20 11:58 | 2015-09-20 16:09 | 2.7175 | 11 | 1445.1481 | 60.2145 | 0.28766 | Sun | Black Carbon
36 | -30 | 0 | S | -2.2083 | 0 | W | 29.8778 | 55.3437 | 15536.8111 | 4488 | 3.0003 | 1.0833 | 2015-09-20 18:52 | 2015-09-20 22:57 | 2.7162 | 11 | 1451.9479 | 60.4978 | 0.28332 | Sun
37 | -30 | 0 | S | -2.7833 | 0 | W | 29.8778 | 55.3437 | 15592.1549 | 4396 | 2.9492 | 1.0833 | 2015-09-21 01:40 | 2015-09-21 05:42 | 2.7162 | 11 | 1458.6965 | 60.779 | 0.28119 | Sun
38 | -30 | 0 | S | -3.3583 | 0 | W | 29.8778 | 55.3437 | 15647.4986 | 4571 | 3.0464 | 1.0833 | 2015-09-21 08:25 | 2015-09-21 12:33 | 2.7162 | 11 | 1465.5424 | 61.0643 | 0.28525 | Sun | Drifter
39 | -30 | 0 | S | -3.9333 | 0 | W | 29.8778 | 55.3437 | 15702.8423 | 4028 | 2.7447 | 1.0833 | 2015-09-21 15:16 | 2015-09-21 19:05 | 2.7162 | 11 | 1472.0866 | 61.3369 | 0.27268 | Sun
40 | -30 | 0 | S | -4.5083 | 0 | W | 29.8778 | 55.3437 | 15758.1861 | 4312 | 2.9025 | 1.0833 | 2015-09-21 21:48 | 2015-09-22 01:47 | 2.7162 | 11 | 1478.7886 | 61.6162 | 0.27925 | Sun
41 | -30 | 0 | S | -5.0833 | 0 | W | 29.8778 | 55.3437 | 15813.5298 | 4142 | 2.8081 | 1.0833 | 2015-09-22 04:30 | 2015-09-22 08:24 | 2.7162 | 11 | 1485.3962 | 61.8915 | 0.27531 | Sun
42 | -30 | 0 | S | -5.6583 | 0 | W | 29.8778 | 55.3437 | 15868.8735 | 4340 | 2.9181 | 1.0833 | 2015-09-22 11:07 | 2015-09-22 15:07 | 2.7162 | 11 | 1492.1138 | 62.1714 | 0.2799 | Sun
43 | -30 | 0 | S | -6.2333 | 0 | W | 29.8778 | 55.3437 | 15924.2172 | 4623 | 3.0753 | 1.0833 | 2015-09-22 17:50 | 2015-09-22 21:59 | 2.7162 | 11 | 1498.9885 | 62.4579 | 0.28645 | Sun
44 | -30.0167 | 0 | S | -6.8083 | 0 | W | 29.8921 | 55.3702 | 15979.5874 | 4087 | 2.7775 | 1.0833 | 2015-09-23 00:42 | 2015-09-23 04:34 | 2.7175 | 11 | 1505.5668 | 62.732 | 0.2741 | Sun
45 | -30 | 0 | S | -7.3833 | 0 | W | 29.8921 | 55.3702 | 16034.9576 | 3939 | 2.6953 | 1.0833 | 2015-09-23 07:17 | 2015-09-23 11:04 | 2.7175 | 11 | 1512.0629 | 63.0026 | 0.27067 | Sun |  | Argo
46 | -30 | 0 | S | -7.9583 | 0 | W | 29.8778 | 55.3437 | 16090.3013 | 4103 | 2.7864 | 1.0833 | 2015-09-23 13:47 | 2015-09-23 17:39 | 2.7162 | 11 | 1518.6488 | 63.277 | 0.27441 | Sun
47 | -30.0167 | 0 | S | -8.5333 | 0 | W | 29.8921 | 55.3702 | 16145.6715 | 4020 | 2.7403 | 1.0833 | 2015-09-23 20:22 | 2015-09-24 00:11 | 2.7175 | 11 | 1525.1899 | 63.5496 | 0.27254 | Sun
48 | -30.0167 | 0 | S | -9.1083 | 0 | W | 29.8728 | 55.3344 | 16201.0059 | 3806 | 2.6214 | 1.0833 | 2015-09-24 02:54 | 2015-09-24 06:37 | 2.7157 | 11 | 1531.6103 | 63.8171 | 0.26752 | Sun
49 | -30 | 0 | S | -9.6833 | 0 | W | 29.8921 | 55.3702 | 16256.3761 | 3907 | 2.6775 | 1.0833 | 2015-09-24 09:20 | 2015-09-24 13:05 | 2.7175 | 11 | 1538.0886 | 64.087 | 0.26993 | Sun
50 | -30 | 0 | S | -10.2583 | 0 | W | 29.8778 | 55.3437 | 16311.7199 | 3832 | 2.6358 | 1.0833 | 2015-09-24 15:48 | 2015-09-24 19:31 | 2.7162 | 11 | 1544.524 | 64.3552 | 0.26814 | Sun |  | Argo
51 | -30 | 0 | S | -10.8333 | 0 | W | 29.8778 | 55.3437 | 16367.0636 | 3625 | 2.5208 | 1.0833 | 2015-09-24 22:14 | 2015-09-25 01:51 | 2.7162 | 11 | 1550.8443 | 64.6185 | 0.26335 | Sun
52 | -30.0167 | 0 | S | -11.4083 | 0 | W | 29.8921 | 55.3702 | 16422.4338 | 3483 | 2.4419 | 1.0833 | 2015-09-25 04:34 | 2015-09-25 08:05 | 2.7175 | 11 | 1557.087 | 64.8786 | 0.26011 | Sun
53 | -30 | 0 | S | -11.9833 | 0 | W | 29.8921 | 55.3702 | 16477.804 | 3598 | 2.5058 | 1.0833 | 2015-09-25 10:48 | 2015-09-25 14:24 | 2.7175 | 11 | 1563.3937 | 65.1414 | 0.26278 | Sun
54 | -30 | 0 | S | -12.5583 | 0 | W | 29.8778 | 55.3437 | 16533.1477 | 3183 | 2.2753 | 1.0833 | 2015-09-25 17:07 | 2015-09-25 20:28 | 2.7162 | 11 | 1569.4684 | 65.3945 | 0.25312 | Sun |  | Argo
55 | -30.0167 | 0 | S | -13.1333 | 0 | W | 29.8921 | 55.3702 | 16588.5179 | 2769 | 2.0453 | 1.0833 | 2015-09-25 23:11 | 2015-09-26 02:19 | 2.7175 | 11 | 1575.3145 | 65.6381 | 0.24359 | Sun
56 | -30 | 0 | S | -13.7083 | 0 | W | 29.8921 | 55.3702 | 16643.8881 | 2446 | 1.8658 | 1.0833 | 2015-09-26 05:02 | 2015-09-26 07:59 | 2.7175 | 11 | 1580.9812 | 65.8742 | 0.23611 | Sun | Black Carbon
57 | -30 | 0 | S | -14.2833 | 0 | W | 29.8778 | 55.3437 | 16699.2318 | 2832 | 2.0803 | 1.0833 | 2015-09-26 10:42 | 2015-09-26 13:52 | 2.7162 | 11 | 1586.8609 | 66.1192 | 0.24499 | Sun
58 | -30 | 0 | S | -14.8583 | 0 | W | 29.8778 | 55.3437 | 16754.5755 | 3527 | 2.4664 | 1.0833 | 2015-09-26 16:35 | 2015-09-26 20:08 | 2.7162 | 11 | 1593.1268 | 66.3803 | 0.26108 | Sun | Drifter | Argo
59 | -30 | 0 | S | -15.4333 | 0 | W | 29.8778 | 55.3437 | 16809.9193 | 3147 | 2.2553 | 1.0833 | 2015-09-26 22:51 | 2015-09-27 02:11 | 2.7162 | 11 | 1599.1816 | 66.6326 | 0.25228 | Sun
60 | -30 | 0 | S | -16.0083 | 0 | W | 29.8778 | 55.3437 | 16865.263 | 3866 | 2.6547 | 1.0833 | 2015-09-27 04:54 | 2015-09-27 08:38 | 2.7162 | 11 | 1605.6358 | 66.9015 | 0.26893 | Sun
61 | -30 | 0 | S | -16.5833 | 0 | W | 29.8778 | 55.3437 | 16920.6067 | 3536 | 2.4714 | 1.0833 | 2015-09-27 11:21 | 2015-09-27 14:54 | 2.7162 | 11 | 1611.9067 | 67.1628 | 0.26129 | Sun
62 | -30.0167 | 0 | S | -17.1583 | 0 | W | 29.8921 | 55.3702 | 16975.9769 | 3920 | 2.6847 | 1.0833 | 2015-09-27 17:37 | 2015-09-27 21:24 | 2.7175 | 11 | 1618.3922 | 67.433 | 0.27023 | Sun
63 | -30 | 0 | S | -17.7333 | 0 | W | 29.8921 | 55.3702 | 17031.3471 | 4025 | 2.7431 | 1.0833 | 2015-09-28 00:07 | 2015-09-28 03:56 | 2.7175 | 11 | 1624.9361 | 67.7057 | 0.27266 | Sun |  | Argo
64 | -30.0167 | 0 | S | -18.3083 | 0 | W | 29.8921 | 55.3702 | 17086.7173 | 4297 | 2.8942 | 1.0833 | 2015-09-28 06:39 | 2015-09-28 10:38 | 2.7175 | 11 | 1631.6311 | 67.9846 | 0.27896 | Sun | Drifter
65 | -30 | 0 | S | -18.8833 | 0 | W | 29.8921 | 55.3702 | 17142.0875 | 3911 | 2.6797 | 1.0833 | 2015-09-28 13:21 | 2015-09-28 17:07 | 2.7175 | 11 | 1638.1116 | 68.2546 | 0.27002 | Sun
66 | -30 | 0 | S | -19.4583 | 0 | W | 29.8778 | 55.3437 | 17197.4312 | 4411 | 2.9575 | 1.0833 | 2015-09-28 19:50 | 2015-09-28 23:52 | 2.7162 | 11 | 1644.8686 | 68.5362 | 0.28154 | Sun
67 | -30 | 0 | S | -20.0333 | 0 | W | 29.8778 | 55.3437 | 17252.7749 | 4522 | 3.0192 | 1.0833 | 2015-09-29 02:35 | 2015-09-29 06:41 | 2.7162 | 11 | 1651.6872 | 68.8203 | 0.28411 | Sun
68 | -30 | 0 | S | -20.6083 | 0 | W | 29.8778 | 55.3437 | 17308.1186 | 4615 | 3.0708 | 1.0833 | 2015-09-29 09:24 | 2015-09-29 13:33 | 2.7162 | 11 | 1658.5576 | 69.1066 | 0.28626 | Sun
69 | -30 | 0 | S | -21.1833 | 0 | W | 29.8778 | 55.3437 | 17363.4624 | 4736 | 3.1381 | 1.0833 | 2015-09-29 16:16 | 2015-09-29 20:30 | 2.7162 | 11 | 1665.4951 | 69.3956 | 0.28906 | Sun | Drifter
70 | -30 | 0 | S | -21.7583 | 0 | W | 29.8778 | 55.3437 | 17418.8061 | 4805 | 3.1764 | 1.0833 | 2015-09-29 23:13 | 2015-09-30 03:28 | 2.7162 | 11 | 1672.471 | 69.6863 | 0.29066 | Sun
71 | -30 | 0 | S | -22.3333 | 0 | W | 29.8778 | 55.3437 | 17474.1498 | 4585 | 3.0542 | 1.0833 | 2015-09-30 06:11 | 2015-09-30 10:19 | 2.7162 | 11 | 1679.3247 | 69.9719 | 0.28557 | Sun
72 | -30 | 0 | S | -22.9083 | 0 | W | 29.8778 | 55.3437 | 17529.4936 | 4604 | 3.0647 | 1.0833 | 2015-09-30 13:02 | 2015-09-30 17:11 | 2.7162 | 11 | 1686.1889 | 70.2579 | 0.28601 | Sun
73 | -30 | 0 | S | -23.4833 | 0 | W | 29.8778 | 55.3437 | 17584.8373 | 4482 | 2.9969 | 1.0833 | 2015-09-30 19:54 | 2015-09-30 23:59 | 2.7162 | 11 | 1692.9854 | 70.5411 | 0.28319 | Sun | Black Carbon
74 | -30 | 0 | S | -24.0583 | 0 | W | 29.8778 | 55.3437 | 17640.181 | 4900 | 3.2292 | 1.0833 | 2015-10-01 02:42 | 2015-10-01 07:01 | 2.7162 | 11 | 1700.014 | 70.8339 | 0.29286 | Sun | Drifter
75 | -30.0167 | 0 | S | -24.6333 | 0 | W | 29.8921 | 55.3702 | 17695.5512 | 5381 | 3.4964 | 1.0833 | 2015-10-01 09:44 | 2015-10-01 14:19 | 2.7175 | 11 | 1707.3112 | 71.138 | 0.30405 | Sun
76 | -30.0167 | 0 | S | -25.2083 | 0 | W | 29.8728 | 55.3344 | 17750.8856 | 5109 | 3.3453 | 1.0833 | 2015-10-01 17:02 | 2015-10-01 21:27 | 2.7157 | 11 | 1714.4555 | 71.4356 | 0.29768 | Sun |  | Argo
77 | -30 | 0 | S | -25.7833 | 0 | W | 29.8921 | 55.3702 | 17806.2558 | 5094 | 3.3369 | 1.0833 | 2015-10-02 00:10 | 2015-10-02 04:36 | 2.7175 | 11 | 1721.5933 | 71.7331 | 0.29741 | Sun
78 | -30 | 0 | S | -26.3583 | 0 | W | 29.8778 | 55.3437 | 17861.5995 | 4810 | 3.1792 | 1.0833 | 2015-10-02 07:19 | 2015-10-02 11:34 | 2.7162 | 11 | 1728.572 | 72.0238 | 0.29078 | Sun
79 | -30 | 0 | S | -26.9333 | 0 | W | 29.8778 | 55.3437 | 17916.9433 | 4743 | 3.1419 | 1.0833 | 2015-10-02 14:17 | 2015-10-02 18:31 | 2.7162 | 11 | 1735.5134 | 72.3131 | 0.28923 | Sun | Drifter
80 | -30 | 0 | S | -27.5083 | 0 | W | 29.8778 | 55.3437 | 17972.287 | 5007 | 3.2886 | 1.0833 | 2015-10-02 21:14 | 2015-10-03 01:36 | 2.7162 | 11 | 1742.6015 | 72.6084 | 0.29534 | Sun
81 | -30 | 0 | S | -28.0833 | 0 | W | 29.8778 | 55.3437 | 18027.6307 | 4507 | 3.0108 | 1.0833 | 2015-10-03 04:19 | 2015-10-03 08:25 | 2.7162 | 11 | 1749.4118 | 72.8922 | 0.28376 | Sun
82 | -30 | 0 | S | -28.4 | 0 | W | 16.4562 | 30.4824 | 18058.1131 | 3745 | 2.5875 | 1.0833 | 2015-10-03 09:54 | 2015-10-03 13:35 | 1.496 | 11 | 1754.5787 | 73.1074 | 0.21529 | Sat
83 | -29.9833 | 0 | S | -29 | 0 | W | 31.1956 | 57.7846 | 18115.8977 | 3160 | 2.2625 | 1.0833 | 2015-10-03 16:25 | 2015-10-03 19:46 | 2.836 | 11 | 1760.7605 | 73.365 | 0.25757 | Sun
84 | -30 | 0 | S | -29.5 | 0 | W | 26.0022 | 48.1648 | 18164.0626 | 2258 | 1.7614 | 1.0833 | 2015-10-03 22:07 | 2015-10-04 00:58 | 2.3638 | 11 | 1765.9691 | 73.582 | 0.21702 | Sun
85 | -30 | 0 | S | -29.8167 | 0 | W | 16.4562 | 30.4824 | 18194.5449 | 3257 | 2.3164 | 1.0833 | 2015-10-04 02:28 | 2015-10-04 05:52 | 1.496 | 11 | 1770.8648 | 73.786 | 0.20399 | Sat
86 | -30 | 0 | S | -30.1667 | 0 | W | 18.1865 | 33.6875 | 18228.2325 | 3784 | 2.6092 | 1.0833 | 2015-10-04 07:31 | 2015-10-04 11:13 | 1.6533 | 11 | 1776.2106 | 74.0088 | 0.22274 | Sat |  | Argo
87 | -30 | 0 | S | -30.7417 | 0 | W | 29.8778 | 55.3437 | 18283.5762 | 4013 | 2.7364 | 1.0833 | 2015-10-04 13:56 | 2015-10-04 17:45 | 2.7162 | 11 | 1782.7465 | 74.2811 | 0.27233 | Sun
88 | -30 | 0 | S | -31.3167 | 0 | W | 29.8778 | 55.3437 | 18338.9199 | 4075 | 2.7708 | 1.0833 | 2015-10-04 20:28 | 2015-10-05 00:19 | 2.7162 | 11 | 1789.3168 | 74.5549 | 0.27376 | Sun
89 | -30 | 0 | S | -31.8917 | 0 | W | 29.8778 | 55.3437 | 18394.2636 | 3954 | 2.7036 | 1.0833 | 2015-10-05 03:02 | 2015-10-05 06:49 | 2.7162 | 11 | 1795.82 | 74.8258 | 0.27096 | Sun
90 | -29.9833 | 0 | S | -32.4667 | 0 | W | 29.8972 | 55.3795 | 18449.6431 | 3736 | 2.5825 | 1.0833 | 2015-10-05 09:32 | 2015-10-05 13:12 | 2.7179 | 11 | 1802.2037 | 75.0918 | 0.26599 | Sun
91 | -30 | 0 | S | -33.0417 | 0 | W | 29.8972 | 55.3795 | 18505.0226 | 3485 | 2.4431 | 1.0833 | 2015-10-05 15:55 | 2015-10-05 19:27 | 2.7179 | 11 | 1808.448 | 75.352 | 0.26018 | Sun
92 | -30 | 0 | S | -33.6167 | 0 | W | 29.8778 | 55.3437 | 18560.3664 | 2942 | 2.1414 | 1.0833 | 2015-10-05 22:10 | 2015-10-06 01:23 | 2.7162 | 11 | 1814.3889 | 75.5995 | 0.24754 | Sun
93 | -30 | 0 | S | -33.9667 | 0 | W | 18.1865 | 33.6875 | 18594.0539 | 2064 | 1.6536 | 1.0833 | 2015-10-06 03:03 | 2015-10-06 05:47 | 1.6533 | 11 | 1818.7792 | 75.7825 | 0.18293 | Sat
94 | -30 | 0 | S | -34.3417 | 0 | W | 19.4856 | 36.0938 | 18630.1476 | 1395 | 1.2819 | 1.0833 | 2015-10-06 07:33 | 2015-10-06 09:55 | 1.7714 | 11 | 1822.9159 | 75.9548 | 0.17236 | Sat
95 | -30 | 0 | S | -34.9167 | 0 | W | 29.8778 | 55.3437 | 18685.4914 | 1863 | 1.5419 | 1.0833 | 2015-10-06 12:38 | 2015-10-06 15:15 | 2.7162 | 11 | 1828.2573 | 76.1774 | 0.22256 | Sun
96 | -30 | 0 | S | -35.4917 | 0 | W | 29.8778 | 55.3437 | 18740.8351 | 2257 | 1.7608 | 1.0833 | 2015-10-06 17:58 | 2015-10-06 20:49 | 2.7162 | 11 | 1833.8177 | 76.4091 | 0.23168 | Sun
97 | -30 | 0 | S | -36.0667 | 0 | W | 29.8778 | 55.3437 | 18796.1788 | 1684 | 1.4425 | 1.0833 | 2015-10-06 23:32 | 2015-10-07 02:04 | 2.7162 | 11 | 1839.0597 | 76.6275 | 0.21842 | Sun
98 | -30 | 0 | S | -36.5333 | 0 | W | 24.2452 | 44.9102 | 18841.0891 | 1852 | 1.5358 | 1.0833 | 2015-10-07 04:16 | 2015-10-07 06:53 | 2.2041 | 11 | 1843.8829 | 76.8285 | 0.20097 | Sun
99 | -30 | 0 | S | -37.15 | 0 | W | 32.0446 | 59.3573 | 18900.4464 | 2290 | 1.7792 | 1.0833 | 2015-10-07 09:48 | 2015-10-07 12:40 | 2.9131 | 11 | 1849.6586 | 77.0691 | 0.24065 | Sun
100 | -30 | 0 | S | -37.4667 | 0 | W | 16.4562 | 30.4824 | 18930.9288 | 2940 | 2.1403 | 1.0833 | 2015-10-07 14:09 | 2015-10-07 17:23 | 1.496 | 11 | 1854.3782 | 77.2658 | 0.19665 | Sat
101 | -30 | 0 | S | -37.5667 | 0 | W | 5.1962 | 9.625 | 18940.5538 | 3462 | 2.4303 | 1.0833 | 2015-10-07 17:51 | 2015-10-07 21:22 | 0.47238 | 11 | 1858.3642 | 77.4318 | 0.16608 | Fri
102 | -30 | 0 | S | -38.0167 | 0 | W | 23.3827 | 43.3125 | 18983.8663 | 3828 | 2.6336 | 1.0833 | 2015-10-07 23:29 | 2015-10-08 03:12 | 2.1257 | 11 | 1864.2068 | 77.6753 | 0.24344 | Sun
103 | -30 | 0 | S | -38.5 | 0 | W | 25.113 | 46.5176 | 19030.3839 | 4186 | 2.8325 | 1.0833 | 2015-10-08 05:29 | 2015-10-08 09:24 | 2.283 | 11 | 1870.4057 | 77.9336 | 0.25828 | Sun
104 | -30.0167 | 0 | S | -38.9167 | 0 | W | 21.6737 | 40.1469 | 19070.5308 | 4231 | 2.8575 | 1.0833 | 2015-10-08 11:23 | 2015-10-08 15:19 | 1.9703 | 11 | 1876.3168 | 78.1799 | 0.2463 | Sat
105 | -30 | 0 | S | -39.3833 | 0 | W | 24.2639 | 44.9448 | 19115.4757 | 4871 | 3.2131 | 1.0833 | 2015-10-08 17:31 | 2015-10-08 21:49 | 2.2058 | 11 | 1882.819 | 78.4508 | 0.27092 | Sun
106 | -30 | 0 | S | -39.5333 | 0 | W | 7.7942 | 14.4375 | 19129.9132 | 3954 | 2.7036 | 1.0833 | 2015-10-08 22:32 | 2015-10-09 02:19 | 0.70857 | 11 | 1887.3146 | 78.6381 | 0.18731 | Fri
107 | -30 | 0 | S | -39.8333 | 0 | W | 15.5885 | 28.875 | 19158.7882 | 3324 | 2.3536 | 1.0833 | 2015-10-09 03:44 | 2015-10-09 07:10 | 1.4171 | 11 | 1892.1686 | 78.8404 | 0.20225 | Sat |  | Argo
108 | -29.8833 | 0 | S | -40.3667 | 0 | W | 28.6028 | 52.9819 | 19211.7701 | 4226 | 2.8547 | 1.0833 | 2015-10-09 09:46 | 2015-10-09 13:42 | 2.6003 | 11 | 1898.7069 | 79.1128 | 0.27243 | Sun
109 | -29.7833 | 0 | S | -40.65 | 0 | W | 15.9193 | 29.4879 | 19241.2581 | 3685 | 2.5542 | 1.0833 | 2015-10-09 15:09 | 2015-10-09 18:47 | 1.4472 | 11 | 1903.7917 | 79.3247 | 0.21186 | Sat
110 | -29.5833 | 0 | S | -41.2167 | 0 | W | 31.8844 | 59.0605 | 19300.3186 | 4071 | 2.7686 | 1.0833 | 2015-10-09 21:41 | 2015-10-10 01:33 | 2.8986 | 11 | 1910.5422 | 79.6059 | 0.28127 | Sun
111 | -29.3833 | 0 | S | -41.8333 | 0 | W | 34.368 | 63.6609 | 19363.9795 | 4077 | 2.7719 | 1.0833 | 2015-10-10 04:40 | 2015-10-10 08:31 | 3.1244 | 11 | 1917.5218 | 79.8967 | 0.29082 | Mon
112 | -29.2167 | 0 | S | -42.375 | 0 | W | 30.0549 | 55.6718 | 19419.6513 | 4018 | 2.7392 | 1.0833 | 2015-10-10 11:15 | 2015-10-10 15:05 | 2.7323 | 11 | 1924.0766 | 80.1699 | 0.27312 | Sun
113 | -29.0167 | 0 | S | -42.95 | 0 | W | 32.4412 | 60.0919 | 19479.7432 | 4016 | 2.7381 | 1.0833 | 2015-10-10 18:02 | 2015-10-10 21:51 | 2.9492 | 11 | 1930.8472 | 80.452 | 0.28211 | Sun
114 | -28.85 | 0 | S | -43.525 | 0 | W | 31.8073 | 58.9177 | 19538.6609 | 3930 | 2.6903 | 1.0833 | 2015-10-11 00:44 | 2015-10-11 04:31 | 2.8916 | 11 | 1937.5124 | 80.7297 | 0.27772 | Sun |  |  | Brazilian EEZ
115 | -28.65 | 0 | S | -44.1 | 0 | W | 32.5405 | 60.2758 | 19598.9367 | 3718 | 2.5725 | 1.0833 | 2015-10-11 07:28 | 2015-10-11 11:08 | 2.9582 | 11 | 1944.1264 | 81.0053 | 0.27559 | Sun
116 | -28.45 | 0 | S | -44.675 | 0 | W | 32.5941 | 60.3752 | 19659.3119 | 3597 | 2.5053 | 1.0833 | 2015-10-11 14:05 | 2015-10-11 17:41 | 2.9631 | 11 | 1950.6781 | 81.2783 | 0.27299 | Sun
117 | -28.2667 | 0 | S | -45.25 | 0 | W | 32.2904 | 59.8126 | 19719.1245 | 3232 | 2.3025 | 1.0833 | 2015-10-11 20:37 | 2015-10-12 | 2.9355 | 11 | 1956.9995 | 81.5416 | 0.26339 | Sun
118 | -28.1333 | 0 | S | -45.7833 | 0 | W | 29.3138 | 54.2989 | 19773.4234 | 2749 | 2.0342 | 1.0833 | 2015-10-12 02:40 | 2015-10-12 05:47 | 2.6649 | 11 | 1962.7818 | 81.7826 | 0.24093 | Sun
119 | -28 | 0 | S | -46.3 | 0 | W | 28.5014 | 52.794 | 19826.2174 | 2255 | 1.7597 | 1.0833 | 2015-10-12 08:22 | 2015-10-12 11:13 | 2.591 | 11 | 1968.2159 | 82.009 | 0.22642 | Sun
120 | -27.95 | 0 | S | -46.4667 | 0 | W | 9.3288 | 17.2801 | 19843.4975 | 1752 | 1.4803 | 1.0833 | 2015-10-12 12:04 | 2015-10-12 14:38 | 0.84808 | 11 | 1971.6276 | 82.1512 | 0.14215 | Fri
121 | -27.9167 | 0 | S | -46.65 | 0 | W | 9.92 | 18.3751 | 19861.8726 | 1259 | 1.2064 | 1.0833 | 2015-10-12 15:32 | 2015-10-12 17:49 | 0.90181 | 11 | 1974.8192 | 82.2841 | 0.13298 | Fri
122 | -27.8667 | 0 | S | -46.8333 | 0 | W | 10.1728 | 18.8434 | 19880.716 | 756 | 0.76028 | 1.0833 | 2015-10-12 18:45 | 2015-10-12 20:35 | 0.9248 | 11 | 1977.5876 | 82.3995 | 0.11535 | Fri
123 | -27.8 | 0 | S | -47.1 | 0 | W | 14.7057 | 27.2399 | 19907.956 | 461 | 0.59639 | 1.0833 | 2015-10-12 21:55 | 2015-10-12 23:36 | 1.3369 | 11 | 1980.6042 | 82.5252 | 0.12569 | Sat
124 | -27.7333 | 0 | S | -47.3833 | 0 | W | 15.564 | 28.8298 | 19936.7857 | 184 | 0.43361 | 1.0833 | 2015-10-13 01:01 | 2015-10-13 02:32 | 1.4149 | 11 | 1983.536 | 82.6473 | 0.12216 | Sat
RIO | -22.75 | 0 | S | -44 | 0 | W | 350.8235 | 649.8421 | 20586.6278 | 0 | 0 | 2 | 2015-10-14 10:26 | 2015-10-14 12:26 | 31.893 | 11 | 2017.4291 | 84.0595 | 1.4122 | Mon | 35.0174 | account for -4 hour time change and allow 6 hours weather time
RIO | -22.75 | 0 | S | -44.01 | 0 | W | 0.1 | 0.18523 | 20586.813 | 0 | 0 | 168 | 2015-10-14 12:26 | 2015-10-21 12:26 | 0.0090909 | 11 | 2185.4382 | 91.0599 | 7.0004 | Fri | 6.0004 | 168
Waypoint | -6.88 | 0 | S | -32.62 | 0 | W | 1157.4558 | 2143.9939 | 22730.807 | 0 | 0 | 0 | 2015-10-25 21:40 | 2015-10-25 21:40 | 105.2233 | 11 | 2290.6614 | 95.4442 | 4.3843 | Fri
Barbados | 13.1333 | 0 | N | -59.65 | 0 | W | 2009.2592 | 3721.8178 | 26452.6248 | 0 | 0 | 0 | 2015-11-02 12:19 | 2015-11-02 12:19 | 182.6599 | 11 | 2473.3213 | 103.0551 | 7.6108 | Fri | 12.9951 | account for -3 hour time change
77.9238
Total Steaming time | [14 empty] | 365.1655 | [5 empty] | 15.2152
Total Wire Time | [10 empty] | 314.9181 | [9 empty] | 13.1216
Total Extra Time | [11 empty] | 136.3333 | [8 empty] | 5.6806
34.0174
Formulas:
Arrival = [Departure, row above]+[steam (h)]/24
Departure = [Arrival]+([wire]+[Extra])/24